## SGRP CA's Action Plan (2019)
INSTITUTIONAL INFRASTRUCTURE AND CAPACITY BUILDING ACTION PLAN OF STRATEGIC GRAIN RESERVES PROJECT (SGRP)
S/N | DESCRIPTION | Duration (Calender days) | 2018 | [11 empty] | 2019 | [11 empty] | 2020 | [11 empty] | 2021 | [11 empty] | 2022 | [5 empty] | REMARK
|  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Q1 |  |  | Q2
|  |  | January | February | March | April | May | June | July | August | September | October | November | December | January | February | March | April | May | June | July | August | September | October | November | December | January | February | March | April | May | June | July | August | September | October | November | December | January | February | March | April | May | June | July | August | September | October | November | December | January | February | March | April | May | June
Component A: Institutional Infrastructure and Capcity Building
1 | A1. Institutional Infrastructure
a | A1.1. Developing Legal Framework | 1080
| Developing SGRC Charter | 90 | [54 empty] | Completed | bar: Q1 January to Q1 March
Incorporating and Reviewing Input on the Charter From Stakeholders | bar: Q2 April to Q3 September
| Processing SGRC Charter with Relevant Stakeholders | 90 | [54 empty] | Completed | bar: Q4 October to Q4 December
| Submitting SGRC Charter to Ministry of Justice | 90 | bar: Q1 January to Q1 March
| Processing SGRC Charter with MoJ | 180 | bar: Q2 April to Q3 September
| Processing SGRC Charter with Ministers’ Council | 90 | bar: Q4 October to Q4 December
| Developing SOP on Procurement of Grains | 90 | bar: Q2 April to Q2 June
| Developing SOP on Storage of Grains | 90 | bar: Q3 July to Q3 September
| Developing SOP on Release of Grains, and Other Instruments as Deemed Necessary | 90 | bar: Q4 October to Q4 December
| Processing SOPs with General Assembly of SGRC | 270 | bar: Q3 July to Q1 March
| A1.2. Institutional Building | 1080
b | Hiring International Consultant for Institutional Infrastructure Assessment of the SGRC | 90 | bar: Q3 July to Q3 September
| Need Assessment and Structural Design (For KBL, KDR & HRT) | 90 | bar: Q4 October to Q4 December
| Procurement of Office Supplies for KDR and HRT Silos | 90 | bar: Q2 April to Q2 June
| Hiring Staff for KDR and HRT Silos | 180 | bar: Q1 January to Q2 June
| Establishing of and Hiring Staff for SGRC HQ in KBL | 180 | bar: Q1 January to Q2 June
| Procurement of Office Supplies for KBL Silos | 90 | bar: Q4 October to Q4 December
| Hiring Staff for MZR and BGL Silos | 90 | bar: Q1 January to Q1 March
| Procurement of Office Supplies for MZR and BGL | 90 | bar: Q1 January to Q1 March
| Hiring Staff for BDK Grain Warehouse | 90 | bar: Q3 July to Q3 September
| Procurement of Office Supplies for BDK Grain Warehouse | 90 | bar: Q3 July to Q3 September
c | A1.3. Capacity Building | 570
| Overseas Visits by SGRP for Observing Best Examples of Strategic Grain Reserves | 120 | bar: Q1 January; Q1 March; Q3 August; Q4 December
| Hiring Int'l Consultant to Conduct Trainng Needs Assessment (TNA) Survey of SGRC | 90 | bar: Q3 September to Q4 November
| Developing Capacity Building Plan as Per the TNA for SGRC | 90 | bar: Q4 December
| Implementing the Capacity Building Plan for SGRC | 180
| Training SGRC and Silos' Staff on SOPs Developed | 90 | bar: Q3 July to Q4 December
| Subcomponet A2: Wheat crop estimation | 360
| Domestic Capacity Building Trainings | 60 | bar: Q1 January to Q1 February
| Int'l Capacity Building Trainings | 60 | bar: Q4 October to Q4 November
| Pre-harvest Wheat Yield Estimation | 60 | bar: Q1 March to Q2 April
| Post-harvest Wheat Yield Estimation | 180 | bar: Q2 April to Q3 September
| Subcomponet A3: Wheat Fortification | 720
| Establish Wheat Fortification Mechanism | 90 | bar: Q3 July to Q3 September
| Fortified Wheat Distributed From Silos | 630 | bar: Q4 October to Q2 June

## SGRP CB's Action Plan (2019)
PHYSICAL INFRUSTRUCTURE ACTION PLAN OF STRATEGIC GRAIN RESERVE PROJECT (SGRP)-2019
S/N | Description | Duration (Working Days) | 2019 | [11 empty] | 2020 | [11 empty] | 2021 | [11 empty] | Remark
|  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4
|  |  | January | February | March | April | May | June | July | August | September | October | November | December | January | February | March | April | May | June | July | August | September | October | November | December | January | February | March | April | May | June | July | August | September | October | November | December
Component B:
Phase-1 | Sub Component B1: Establishment of Grain Steel Silos in Kabul (50,000 MT) | 730 | bar: Q1 January to Q3 September; Q1 January to Q3 September; Q1 January to Q3 September
| B1.1. Preparation of Technical Specification for Design Build Project | 95 | [36 empty] | Completed | bar: Q1 January to Q3 September; Q1 January to Q3 September; Q1 January to Q3 September
| B1.2. NOL/Proc. Phase (Tendering Process) | 95 | bar: Q1 January to Q3 September; Q1 January to Q3 September; Q1 January to Q3 September
| B1.3. Design,Construction and Installaton | 540 | bar: Q1 January to Q3 September; Q1 January to Q3 September; Q1 January to Q3 September
| Sub Component B3: Establishment of Grain Steel Silos in Herat (20,000 MT) | 497 | bar: Q1 January to Q3 September; Q1 January to Q3 September; Q1 January to Q3 September
| B3.1. Preparation of Technical Specification for Design Build Project | 37 | [36 empty] | Completed | bar: Q1 January to Q3 September; Q1 January to Q3 September; Q1 January to Q3 September
| B3.2. NOL/Proc. Phase (Tendering Process) | 95 | bar: Q1 January to Q3 September; Q1 January to Q3 September; Q1 January to Q3 September
| B3.3. Design,Construction and Installaton | 365 | bar: Q1 January to Q3 September; Q1 January to Q3 September; Q1 January to Q3 September
| Sub Component B5: Establishment of Grain Steel Silos in Kandahar (20,000 MT) | 497 | bar: Q1 January to Q3 September; Q1 January to Q3 September; Q1 January to Q3 September
| B5.1. Preparation of Technical Specification for Design Build Project | 37 | [36 empty] | Completed | bar: Q1 January to Q3 September; Q1 January to Q3 September; Q1 January to Q3 September
| B5.2. NOL/Proc. Phase (Tendering Process) | 95 | bar: Q1 January to Q3 September; Q1 January to Q3 September; Q1 January to Q3 September
| B1.4. Design,Construction and Installaton | 365 | bar: Q1 January to Q3 September; Q1 January to Q3 September; Q1 January to Q3 September