## Sheet1
Annual Work Plan (AWP) | [10 empty] | Restricted Area - Please do not delete
(00097936) - Community Based Agriculture and Rural Development - West (CBARD-West)
Year : (2020)
Key Result Area (from 2018-21 Strategic Plan): | Outcome 1 : Eradicate Poverty in all its forms and dimensions
ONE UN Outcome | Outcome 5.1: Access to basic services is increased and community resilience and social cohesion enhanced
NPP Cluster: | Cluster 1: AGRICULTURE AND RURAL DEVELOPMENT CLUSTER
National Priority Programmes: | NPP 1.1: National Water and Natural Resource Development.
NPP Component: | Cross-cutting component (Counter Narcotics)
Related CPD Outcome: | Outcome 3: Economic growth is accelerated to reduce vulnerabilities and poverty, strengthen the resilience of the licit economy and reduce the illicit economy in its multiple dimensions.
CPD indicators, baseline and targets: | Baseline: 36.3% (29.1% urban, 36.9% rural)
Target: 2% reduction in the overall poverty rate
Indicator: Poverty headcount
Related CPD Output/s: | Output 6: Improved economic livelihoods, especially for vulnerable populations and women.
Tokyo Mutual Accountability Framework (TMAF) Area: | Area 5: inclusive and sustainable development
New Deal Area: | PSG 4: Economic Foundations
Programme Cluster: | Livelihoods and Resilience
Project Modality: (NIM/DIM) | NIM | Implementing Partner (IP): |  |  |  |  | Ministry of Agriculture, Irrigation and Livestock (MAIL)
On-budget/Off-budget: | On-budget: | 0 | Off-budget: |  | 8874595.7978 |  | Funding Modality | Cost Sharing |  | 8874595.7978
Output 1 (Atlas Output# 00101474): Local production of, and market for, high-value crops improved
NPP Sub-components | 1. Horticulture (Value Chain) 2. Women in Agriculture 3. Irrigation
Indicators: 1.1. # of communities identified for intervention and control group in Badghis and Farah 1.2. # of high value crops identified in targeted communities 1.3. Value chain study in-place for identified high value agricultural products 1.4. # of communities that implement the gender sensitive business models for high-value agricultural products 1.5. Number of women and men trained in gender sensitive agro-business development in all 63 treatment communities 1.6. Degree of usefulness to the local communities of the proposed gender sensitive business models (Scale: unusable, partially useful, useful, mostly useful, completely useful) 1.7. # of women and men trained on value-add steps in targeted communities 1.8. # of people which implement the climate change adaptable agricultural inputs and utilize the technology provided 1.9. # of people which directly benefit by hosting the Field Farmer Schools (FFS) on their land in target communities 1.10. # of local agricultural production monitoring systems rehabilitated or established in targeted communities 1.11. Rural financing mechanisms established (Yes/No) 1.12. # of pre-harvest horticulture-tools package provided to farmers 1.13. #/list of VA equipment provided for selected high value agricultural products 1.14. # of business entities participated in national and International trade/agriculture Fairs 1.15. Productivity of high-value agricultural crops (kg per ha) (Newly added from RRF) 1.16. Gross margin per ha of high-value agricultural products resulting from value chain interventions (Afs per kg) (Newly added from RRF) 1.17. Total land area cultivated under high-value licit crops (ha) and illicit crops (land use maps) (Newly added from RRF) | [5 empty] | Baseline: 2020 1.1. Completed 1.2. Completed 1.3. Yes (completed) 1.4. 63 (7 communities suspended and not workable anymore) 1.5. 1,500 people total (420 F, 1,080 M) 1.6. Not applicable anymore (to be removed in MTE) 1.7. 900 people total (220 F, 680 M) 1.8. 63 (7 communities suspended and not workable anymore) 1.9. 2,070 people total (662 F, 1,408 M) 1.10. 1 (Completed) 1.11. Not applicable anymore (to be removed in MTE) 1.12. 2,190 packages total 1.13. 860 items total 1.14. 60 total 1.15. Pom: 11,100, App: 15,000, Pist: 60: Grp: 16,650, GH Crops: 40,000 1.16. Pom: 293K, App: 591K , Pist: 10K: Grp: 358K, GH Crops: 249K 1.17. Licit: 6,199, Illicit: 9,687 |  |  | Annual Targets: (2020) 1.1. Completed 1.2. Completed 1.3. Yes (completed) 1.4. 63 (7 communities suspended and not workable anymore) 1.5. 2,100 people total (630 W, 1,470 M) = 600 (120 F, 480 M) additional 1.6. Not applicable anymore (to be removed in MTE) 1.7. 1,500 people total (450 W, 1,050 M) = 600 (120 F, 480 M) additional) 1.8. 63 (7 communities suspended and not workable anymore) 1.9. 2,670 people total (801 W, 1,890 M) = 600 (120 F, 480 M) additional 1.10.1 (Completed) 1.11. Not applicable anymore (to be removed in MTE) 1.12. 3,090 total = 900 additional 1.13. 1,010 total = 150 additional 1.14. 80 total = 20 additional 1.15. Pom: 22,200, App: 55,000, Pist: 150: Grp: 24,975, GH Crops: 40,000 1.16. Pom: 572K, App: 1,681K , Pist: 61K: Grp: 611K, GH Crops: 168K 1.17. Licit: 6,478, Illicit: 9,408
PLANNED ACTIVITIES | Actions / Inputs Description | TIMEFRAME |  |  |  | RESPONSIBLE PARTY | PLANNED BUDGET
PLANNED ACTIVITIES | Associated Actions/Results | Q1 | Q2 | Q3 | Q4 | RESPONSIBLE PARTY | Donor | Fund Code | Budget Account & Description | 2019 ($) | Output | Activity
Activity Result 1.1: Identify beneficiary communities and applicable high-value agricultural products (Inception Phase) | Action1.1.3 Develop (analysis and design) value chain for the identified high value agricultural products including: Product flow/actor mapping, Marketing, Business Development, Horizontal Linkages, Vertical Linkages, Commercial Support, Non-commercial Support Action1.1.4 Identify/initiate contact with relevant input suppliers, farmer groups, cooperatives, agro-based enterprises, producer groups and SMEs Activity 1.1.5 Map existing financing opportunities (baseline) within 70 communities in collaboration with local funding organizations / banks, and suppliers, farmer groups, cooperatives, agro-based enterprises, producer groups, SMEs and Entrepreneurs Activity 1.1.6. Identify and select Micro Finance Institutions (MFI) to provide and manage financing mechanisms including Sharia-Compliant products . 'General Management Services (GMS) 8% | X | X | X | X | MAIL | 11710 | 30000 | 71300 - Local Consultants | 0 | 101474 | 1.1
|  | X | X | X | X | MAIL | 11710 | 30000 | 72100 - Contractual Services-Companies | 0 | 101474 | 1.1
|  | X | X | X | X | MAIL | 11710 | 30000 | 75100 - Facilities & Administration | 0 | 101474 | 1.1
Subtotal Activity Result 1.1.: | [9 empty] | 0
Activity Result 1.2: Put in place appropriate gender sensitive business model(s) with strong linkage between farms and markets for high value agricultural products. | Action1.2.1 Develop gender sensitive agro-business development training modules 'Action1.2.2 Deliver a four-day gender sensitive agro-business development training modules for identified farmer groups, cooperatives, agro-based enterprises, producer groups and SMEs (DSA, transportation, refreshment and training material cost for 900 trainees) Action1.2.3 Provide horticulture-tools package to participants of the trainings (locally purchased Pruning scissors, pruning sheers, pruning saw, knapsack sprayer, duster, harvesting bag, complete protective clothes, ladders, and fruit trees budding knife). Action1.2.4 Develop and present appropriate gender sensitive business development plans (BDPs to the identified farmer groups, cooperatives, agro-based enterprises, producer groups and SMEs. Action1.2.5 Identify and provide value-addition equipment and gender sensitive training for the selected high value agricultural products (Grading, Sorting, Packaging and Labeling) which can be done locally by both women and men 'General Management Services (GMS) 8% | X | X | X | X | MAIL | 11710 | 30000 | 71300 - Local Consultants | 110476.8 | 101474 | 1.2
|  | X | X | X | X | MAIL | 11710 | 30000 | 72300 - Materials & Goods | 909500 | 101474 | 1.2
|  | X | X | X | X | MAIL | 11710 | 30000 | 74100 - Professional Services | 60000 | 101474 | 1.2
|  | X | X | X | X | MAIL | 11710 | 30000 | 75700 - Training, Workshops and Confer | 290500 | 101474 | 1.2
|  | X | X | X | X | MAIL | 11710 | 30000 | 75100 - Facilities & Administration | 109638.144 | 101474 | 1.2
|  | X | X | X | X | UNDP | 11710 | 30000 | 71200 - International Consultants | 12150 | 101474 | 1.2
|  | X | X | X | X | UNDP | 11710 | 30000 | 75100 - Facilities & Administration | 972 | 101474 | 1.2
Subtotal Activity Result 1.2.: | [9 empty] | 1493236.944
Activity Result 1.3: Provide climate change adaptable agricultural inputs along with inexpensive, readily available and simple technology | Action1.3.1 Design gender responsive Farmer Field School (FFS) programs for key community members (Lead Farmers) (to include 20% female head of households, 15% marginalized minorities) 1. making of compost exhibitions; 2. Integrated Pest Management (Organic control); 3. mulching; 4. intercropping; and 5. climate change and disaster risk reduction community awareness Action1.3.2 Implement 30 gender responsive Farmer Field School (FFS) programme for Lead farmers (to include 20% female head of households, 15% marginalized minorities) with needed martials on: 1. making of compost exhibitions; 2. Integrated Pest Management (Organic control); 3. mulching; 4. intercropping; and 5. climate change and disaster risk 'General Management Services (GMS) 8% | X | X | X | X | MAIL | 11710 | 30000 | 71300 - Local Consultants | 31763.84 | 101474 | 1.3
|  | X | X | X | X | MAIL | 11710 | 30000 | 72100 - Contractual Services-Companies | 814000 | 101474 | 1.3
|  | X | X | X | X | MAIL | 11710 | 30000 | 72300 - Materials & Goods | 274200 | 101474 | 1.3
|  | X | X | X | X | MAIL | 11710 | 30000 | 75700 - Training, Workshops and Confer | 108000 | 101474 | 1.3
|  | X | X | X | X | MAIL | 11710 | 30000 | 75100 - Facilities & Administration | 98237.1072 | 101474 | 1.3
|  | X | X | X | X | UNDP | 11710 | 30000 | 71200 - International Consultants | 12150 | 101474 | 1.3
|  | X | X | X | X | UNDP | 11710 | 30000 | 75100 - Facilities & Administration | 972 | 101474 | 1.3
Subtotal Activity Result 1.3.: | [9 empty] | 1339322.9472
Activity Result 1.4: Establish Area, Production and Yield (APY) crop pattern monitoring system for 30 target communities | Action 1.4.1. Conduct APY baseline survey in 30 communities and develop APY database. 'Action1.4.2 Analyze APY bi-annual data against baseline and maintain the APY database 'General Management Services (GMS) 8% | X | X | X | X | MAIL | 11710 | 30000 | 71300 - Local Consultants | 106364.344 | 101474 | 1.4
|  | X | X | X | X | MAIL | 11710 | 30000 | 71600 - Travel | 10000 | 101474 | 1.4
|  | X | X | X | X | MAIL | 11710 | 30000 | 75100 - Facilities & Administration | 9309.1475 | 101474 | 1.4
|  | X | X | X | X | UNDP | 11710 | 30000 | 71200 - International Consultants | 12150 | 101474 | 1.4
|  | X | X | X | X | UNDP | 11710 | 30000 | 75100 - Facilities & Administration | 972 | 101474 | 1.4
Subtotal Activity Result 1.4: | [9 empty] | 138795.4915
Activity Result 1.5: Project Management, monitoring, and reporting | Project Management, monitoring, and reporting activities Audit Fee 'General Management Services (GMS) 8% | X | X | X | X | MAIL | 11710 | 30000 | 71300 - Local Consultants | 260571.636 | 101474 | 1.5
|  | X | X | X | X | MAIL | 11710 | 30000 | 71600 - Travel | 10000 | 101474 | 1.5
|  | X | X | X | X | MAIL | 11710 | 30000 | 72200 - Equipment and Furniture | 350 | 101474 | 1.5
|  | X | X | X | X | MAIL | 11710 | 30000 | 72300 - Materials & Goods | 3600 | 101474 | 1.5
|  | X | X | X | X | MAIL | 11710 | 30000 | 72400 - Communic & Audio Visual Equip | 10800 | 101474 | 1.5
|  | X | X | X | X | MAIL | 11710 | 30000 | 72500 - Supplies | 3600 | 101474 | 1.5
|  | X | X | X | X | MAIL | 11710 | 30000 | 72800 - Information Technology Equipmt | 4900 | 101474 | 1.5
|  | X | X | X | X | MAIL | 11710 | 30000 | 73100 - Rental & Maintenance-Premises | 4200 | 101474 | 1.5
|  | X | X | X | X | MAIL | 11710 | 30000 | 73400 - Rental & Maint of Other Equip | 9600 | 101474 | 1.5
|  | X | X | X | X | MAIL | 11710 | 30000 | 75100 - Facilities & Administration | 24609.7309 | 101474 | 1.5
|  | X | X | X | X | UNDP | 11710 | 30000 | 62300 - Recurrent Payroll Costs-IP Stf | 61890 | 101474 | 1.5
|  | X | X | X | X | UNDP | 11710 | 30000 | 64300 - Staff Mgmt Costs - IP Staff | 66784.425 | 101474 | 1.5 | Original
|  | X | X | X | X | UNDP | 11710 | 30000 | 71400 - Contractual Services - Individ | 22086.084 | 102012 | 1.5
|  | X | X | X | X | UNDP | 11710 | 30000 | 71200 - International Consultants | 24000 | 101474 | 1.5
|  | X | X | X | X | UNDP | 11710 | 30000 | 71300 - Local Consultants | 7500 | 101474 | 1.5
|  | X | X | X | X | UNDP | 11710 | 30000 | 71600 - Travel | 10000 | 101474 | 1.5
|  | X | X | X | X | MAIL | 11710 | 30000 | 74100 - Professional Services | 17500 | 101474 | 1.5
|  | X | X | X | X | UNDP | 11710 | 30000 | 74500 - Miscellaneous Expenses | 27424.5003 | 101474 | 1.5
|  | X | X | X | X | UNDP | 11710 | 30000 | 75100 - Facilities & Administration | 83962.1607 | 101474 | 1.5
Subtotal Activity Result 1.5: | [9 empty] | 653378.5369
Output 1 Total: | [9 empty] | 3624733.9197
Output 2 (Atlas Output# 00102012): Community-based agro-business infrastructures (irrigation, transportation, agricultural facilities) are built, developed, and/or strengthened
NPP Sub-components | 1. Horticulture (Value Chain) 2. Women in Agriculture 3. Irrigation
Indicators: 2.1. # of community-based agricultural and agro-business infrastructure identified 2.2. # of community-based agricultural and agro-business infrastructure identified (same as 2.1) 2.3. # of persons trained on mobilization of local resources, project planning, implementation and monitoring in target communities (M/F) 2.4. # of local mobilization campaigns implemented in targeted communities 2.5. # of training Needs Assessments Conducted on project management, implementation and monitoring. 2.6. # of community-based agricultural infrastructures constructed or installed in target communities 2.7. # of business oriented agro-business infrastructures constructed or installed in targeted communities 2.8. # of households in Farah and Badghis provinces reached by the Counter Narcotics campaign 2.9 # of community members targeted by mobile based messages in targeted communities 2.10. Hectares of land irrigated by project interventions (Newly added from RRF) 2.11. Change in farm income from production of high-value crops and added value from drying and storage (Newly added from RRF) |  | Baseline: 2020 2.1. 733 total (65 raisin houses, 460 greenhouses, 40 micro greenhouses, 43 irrigation structures, 70 ha grape trellises, 30 cold storage units, 25 onion cold storage units) = 206 (15 Raisin Houses, 71 Greenhouses, 40 Micro greenhouses, 15 Irrigation, 20 hectares of Grape Trellising, 20 underground Cold Storages, 25 onion cold storages) additional 2.2. same as above 2.3. 880 people (176 F, 704 M) 2.4. Not applicable 2.5. 3 developed (Completed) 2.6. 765 total (65 raisin houses, 490 greenhouses, 40 micro greenhouses, 45 irrigation structures, 70 ha grape trellises, 30 cold storage units, 25 onion cold storage units) 2.7. same as above 2.8. 7000 (100/per community) 2.9. 2100 (30 per community) 2.10. 637 2.11. 20% | [6 empty] | Annual Targets: (2020) 2.1. 939 total = 206 (15 Raisin Houses, 71 Greenhouses, 40 Micro greenhouses, 15 Irrigation, 20 hectares of Grape Trellising, 20 underground Cold Storages, 25 onion cold storages) additional 2.2. same as above 2.3. 1,480 people total (296 W, 1,184 M) = 600 (120 F, 480 M) additional 2.4. Not applicable 2.5. 3 developed (Completed) 2.6. 971 total = 206 (15 Raisin Houses, 71 Greenhouses, 40 Micro greenhouses, 15 Irrigation, 20 hectares of Grape Trellising, 20 underground Cold Storages, 25 onion cold storages) additional 2.7. same as above 2.8. 7000 (100/per community) 2.9. 2100 (30 per community) 2.10. 849 2.11. 20%
PLANNED ACTIVITIES | Actions / Inputs Description | TIMEFRAME |  |  |  | RESPONSIBLE PARTY | PLANNED BUDGET
| Associated Actions/Results | Q1 | Q2 | Q3 | Q4 |  | Donor | Fund Code | Budget Account & Description | 2019 ($)
Activity Result 2.1: Assess and prioritize community-based agricultural and agro-business infrastructure needs in collaboration with communities and in reference to DDPs | Action2.1.1 Assess community-based agricultural and agro-business infrastructure needs ' Action2.1.2 Analyze assessments to list cost effective community-based agricultural input and agro-business infrastructure needs 'Action2.1.3 In collaboration with DDAs, CDCs, women and men, youth and marginalized groups of the selected communities prioritize the cost effective community-based agricultural and agro-business intervention options for 30 communities and update 5 District Development Plans (DDPs) 'General Management Services (GMS) 8% | X | X | X | X | MAIL | 11710 | 30000 | 71300 - Local Consultants | 9794.88 | 102012 | 2.1
|  | X | X | X | X | MAIL | 11710 | 30000 | 75100 - Facilities & Administration | 783.5904 | 102012 | 2.1
Subtotal Activity Result 2.1: | [9 empty] | 10578.4704
Activity Result 2.2: Mobilize community contributions for implementation and sustainability of the agro-based infrastructures | Action2.2.1 Develop a training module for CDCs/DDAs to mobilize land donations for agricultural inputs which strengthen the community at large (irrigation facilities, water reservoirs, etc.), agro business infrastructure (for farmer organizations, and SMEs), materials for construction, needed equipment, as well as unskilled, semi-skilled and skilled labour contributions from both women and men (as per community contracting) 'Action2.2.2 Implement a training module for CDCs (20% women) to campaign for local contributions (2 days training module) 'Action2.2.3 Provincial project staff in coordination with CDCs implement local community contribution campaigns (Awareness material, local radio announcement, SMS, IVR) 'General Management Services (GMS) 8% | X | X | X | X | MAIL | 11710 | 30000 | 71300 - Local Consultants | 30611.52 | 102012 | 2.2
|  | X | X | X | X | MAIL | 11710 | 30000 | 75700 - Training, Workshops and Confer | 108000 | 102012 | 2.2
|  | X | X | X | X | MAIL | 11710 | 30000 | 75100 - Facilities & Administration | 11088.9216 | 102012 | 2.2
Subtotal Activity Result 2.2: | [9 empty] | 149700.4416
Activity Result 2.3: Ensure local projects properly managed and monitored by CDCs and DDAs | Action2.3.1 Conduct training need assessment (TNA) among CDCs, and DDAs in project management, implementation, and monitoring 'Action2.3.2 Develop training modules based on the findings of the TNA 'Action2.3.3 Deliver training modules based on the findings of the TNA 'General Management Services (GMS) 8% | X | X | X | X | MAIL | 11710 | 30000 | 71300 - Local Consultants | 34312.48 | 102012 | 2.3
|  | X | X | X | X | MAIL | 11710 | 30000 | 75700 - Training, Workshops and Confer | 108000 | 102012 | 2.3
|  | X | X | X | X | MAIL | 11710 | 30000 | 75100 - Facilities & Administration | 11384.9984 | 102012 | 2.3
Subtotal Activity Result 2.3: | [9 empty] | 153697.4784
Activity Result 2.4: Implement agreed upon community-based agricultural and agro-business infrastructure projects | Action2.4.1 Construction of community-based agricultural infrastructure (irrigation canals and systems, protection walls, etc.) and interventions 'Action2.4.2 Construction of community-based agro-business infrastructure (packaging centers, sorting and storage sites, cold storage, etc.) 'General Management Services (GMS) 8% | X | X | X | X | MAIL | 11710 | 30000 | 71300 - Local Consultants | 127352.56 | 102012 | 2.4
|  | X | X | X | X | MAIL | 11710 | 30000 | 72100 - Contractual Services-Companies | 3006476.1905 | 102012 | 2.4
|  | X | X | X | X | MAIL | 11710 | 30000 | 75100 - Facilities & Administration | 250706.3 | 102012 | 2.4
|  | X | X | X | X | UNDP | 11710 | 30000 | 71200 - International Consultants | 12150 | 102012 | 2.4
|  | X | X | X | X | UNDP | 11710 | 30000 | 75100 - Facilities & Administration | 972 | 102012 | 2.4
Subtotal Activity Result 2.4: | [9 empty] | 3397657.0505
Activity Result 2.5: Implement a Counter Narcotics campaign | Action2.5.1 Develop a counter narcotics public awareness raising campaign (animations, local radio announcement, posters, brochures, banners, notebook for school children, mobile messages i.e. SMS and IVRs) Action2.5.2 Implement counter narcotics public awareness raising campaign 'Action2.5.3 Establish SMS, IVR, app-based farmer call center to deliver (send and receive) mobile based informative messages on counter narcotics awareness, early warning, crop calendar tracking and agro extension. The platform will include communities Area, Production and Yield (APY) crop pattern database, communities demography, farmers contact list, case management and reporting tools 'General Management Services (GMS) 8% | X | X | X | X | MAIL | 11710 | 30000 | 71300 - Local Consultants | 13200.752 | 102012 | 2.5
|  | X | X | X | X | MAIL | 11710 | 30000 | 72100 - Contractual Services-Companies | 206666 | 102012 | 2.5
|  | X | X | X | X | MAIL | 11710 | 30000 | 75100 - Facilities & Administration | 17589.3402 | 102012 | 2.5
Subtotal Activity Result 2.5: | [9 empty] | 237456.0922
Activity Result 2.6: Project Management, monitoring, and reporting | Project Management, monitoring, and reporting activities Audit Fee 'General Management Services (GMS) 8% | X | X | X | X | MAIL | 11710 | 30000 | 71300 - Local Consultants | 260571.636 | 102012 | 2.6
|  | X | X | X | X | MAIL | 11710 | 30000 | 71600 - Travel | 10000 | 102012 | 2.6
|  | X | X | X | X | MAIL | 11710 | 30000 | 72200 - Equipment and Furniture | 350 | 102012 | 2.6
|  | X | X | X | X | MAIL | 11710 | 30000 | 72300 - Materials & Goods | 3600 | 102012 | 2.6
|  | X | X | X | X | MAIL | 11710 | 30000 | 72400 - Communic & Audio Visual Equip | 10800 | 102012 | 2.6
|  | X | X | X | X | MAIL | 11710 | 30000 | 72500 - Supplies | 3600 | 102012 | 2.6
|  | X | X | X | X | MAIL | 11710 | 30000 | 72800 - Information Technology Equipmt | 4900 | 102012 | 2.6
|  | X | X | X | X | MAIL | 11710 | 30000 | 73100 - Rental & Maintenance-Premises | 4200 | 102012 | 2.6
|  | X | X | X | X | MAIL | 11710 | 30000 | 73400 - Rental & Maint of Other Equip | 9600 | 102012 | 2.6
|  | X | X | X | X | MAIL | 11710 | 30000 | 75100 - Facilities & Administration | 24609.7309 | 102012 | 2.6
|  | X | X | X | X | UNDP | 11710 | 30000 | 62300 - Recurrent Payroll Costs-IP Stf | 61890 | 108120 | 2.6
|  | X | X | X | X | UNDP | 11710 | 30000 | 64300 - Staff Mgmt Costs - IP Staff | 66784.425 | 102012 | 2.6 | Original
|  | X | X | X | X | UNDP | 11710 | 30000 | 71200 - International Consultants | 24000 | 102012 | 2.6
|  | X | X | X | X | UNDP | 11710 | 30000 | 71300 - Local Consultants | 7500 | 102012 | 2.6
|  | X | X | X | X | UNDP | 11710 | 30000 | 71400 - Contractual Services - Individ | 22086.084 | 102012 | 2.6
|  | X | X | X | X | UNDP | 11710 | 30000 | 71600 - Travel | 10000 | 102012 | 2.6
|  | X | X | X | X | UNDP | 11710 | 30000 | 74100 - Professional Services | 17500 | 102012 | 2.6
|  | X | X | X | X | UNDP | 11710 | 30000 | 74500 - Miscellaneous Expenses | 27424.5003 | 102012 | 2.6
|  | X | X | X | X | UNDP | 11710 | 30000 | 75100 - Facilities & Administration | 18974.8007 | 102012 | 2.6
Subtotal Activity Result 2.6: | [9 empty] | 588391.1769
Output 2 Total: | [9 empty] | 4537480.71
Output 3 (Atlas Output# ): Potential Markets (including national and international) for CBARD products established.
NPP Sub-components | 1. Improve crop quality for major domestic and international markets 2. Improve demand for CBARD areas' crops 3 Project management, reporting, monitoring
Indicators: 3.1. Volume of agricultural products from CBARD project areas sold in major domestic and international markets (tons) (Newly Added from RRF) 3.2. Value of agricultural products sold at major domestic and international markets (US Dollars)(Newly Added from RRF) 3.3. Percent of production from CBARD areas sold into international markets (Newly Added from RRF) |  | Baseline: (2019) 3.1. 0 3.2. 0 3.3. 0 | [6 empty] | Annual Targets: (2019) 3.1. 250 Major Domestic, 1,000 International 3.2. $125,000 Major Domestic, $1,000,000 International 3.3. 20%
PLANNED ACTIVITIES | Actions / Inputs Description | TIMEFRAME |  |  |  | RESPONSIBLE PARTY | PLANNED BUDGET
| Associated Actions/Results | Q1 | Q2 | Q3 | Q4 |  | Donor | Fund Code | Budget Account & Description | 2020 ($)
Activity Result 3.1. CBARD crop quality is improved to meet domestic and international market standards | 3.1.1. Input Supplies: Provide advance information to input suppliers in district centres, provincial capitals or elsewhere on input requirements for CBARD crops. 3.1.2. Extension: Master trainers train CBARD and MAIL extension staff on quality, quantity and time of production to meet market requirements. 3.1.3. Cropping Changes: Conduct market analysis at international and national markets and identify best crops and market windows. 3.1.4. Cropping Changes: Share information with traders and with the farmers through the groups and master trainers 3.1.5. Train farmers on both horticultural pre-harvest, harvest, and post-harvest techniques that fulfil desired market requirements. | - | - | x | x | ROP | 11710 | 3000 | 71200 - International Consultants | 86033.2676 |  | 3.1
|  | - | - | x | x | ROP | 11710 | 3000 | 71300 - National Consultants | 56123.6256 |  | 3.1
|  | - | - | x | x | ROP | 11710 | 3000 | 71600 - Travel | 18787.5 |  | 3.1
|  | - | - | x | x | UNDP | 11710 | 3000 | 75100 - Facilities & Administration | 12875.5515 |  | 3.1
[9 empty] | Subtotal Activity Result 3.1 | 173819.9447
Activity Result 3.2. Demand for CBARD supported crops increased | 3.2.1. Group Collection: Analysis of needs for, and characteristics of, collection sites by crop. 3.2.2. Processing: Analysis of the quantity, quality and time requirements for raisins. 3.2.3. Processing: Analysis of the need for packhouses/pre-chiller structures as per the need of different crops. 3.2.4. Processing: Link with existing packhouses or pre-chiller infrastructures 3.2.5. Processing: Provide incentives for traders such as covering costs of freight or packing. 3.2.6. Processing: Train traders on the standards required for exports 3.2.7. Market Analysis: Value chain analysis of CBARD crops in export markets. 3.2.8. Market Analysis: Identify target markets for CBARD crops. 3.2.9. Business Linkages: Identify Afghan traders interested in, and capable of, exporting to target markets as well as trading at national level for crops that are not exportable, educate them on market requirements and sign MOUs. 3.2.10. Business Linkages: Provide financial incentives for traders to enter target markets. 3.2.11. Shipping Documentation Requirements: Technical requirements for each CBARD crop in each target market will be identified, traders trained and supported for compliance | - | - | x | x | ROP | 11710 | 3000 | 71200 - International Consultants | 86033.2676 |  | 3.2
|  | - | - | x | x | ROP | 11710 | 3000 | 71300 - National Consultants | 38413.727 |  | 3.2
|  | - | - | x | x | ROP | 11710 | 3000 | 71600 - Travel | 18787.5 |  | 3.2
|  | - | - | x | x | ROP | 11710 | 3000 | 72300 - Materials and Goods | 114750 |  | 3.2
|  | - | - | x | x | UNDP | 11710 | 3000 | 75100 - Facilities & Administration | 20638.7596
[9 empty] | Subtotal Activity Result 3.2 | 278623.2542
3.3 Project management, reporting, monitoring | Project Management, monitoring, and reporting activities Audit Fee 'General Management Services (GMS) 8% | - | - | x | x | ROP | 11710 | 3000 | 71300 - National Consultants | 98223.1424 |  | 3.3
|  | - | - | x | x | ROP | 11710 | 3000 | 71600 - Travel | 12000 |  | 3.3
|  | - | - | x | x | ROP | 11710 | 3000 | 72100 - Contractual Services-Companies | 66860.1624 |  | 3.3
|  | - | - | x | x | ROP | 11710 | 3000 | 72200 - Equipment and Furniture | 10800 |  | 3.3
|  | - | - | x | x | ROP | 11710 | 3000 | 72500 - Supplies | 31500 |  | 3.3
|  | - | - | x | x | ROP | 11710 | 3000 | 72800 - Information Technology Equipment | 10500 |  | 3.3
|  | - | - | x | x | ROP | 11710 | 3000 | 73100 - Rental & Maintenance - Premises | 9000 |  | 3.3
|  | - | - | x | x | ROP | 11710 | 3000 | 74500 - Miscellaneous Expenses | 1800 |  | 3.3
|  | - | - | x | x | UNDP | 11710 | 3000 | 75100 - Facilities & Administration | 19254.6644
[9 empty] | Subtotal Activity Result 3.3 | 259937.9692
Output 3 Total: | [9 empty] | 712381.1681
[9 empty] | Total Project 2020 | 8874595.7978
Project Tolerance (the permissible deviation from a plan - in terms of time and cost without bringing the deviation to the attention of the the Project Board/Steering Committee:) | [9 empty] | 10%
This Annual Work Plan (AWP) is based on Programme and Operations Policies and Procedures (POPP) and Results Based Management (RBM) guidelines of UNDP. Once signed by UNDP and the implementing partner, the plan authorizes the responsible parties and project management to manage available resources and achieve set results.
Project Manager | Government Counterpart | [7 empty] | UNDP
Name: | Name: Nasir Ahmad Durrani, Minister - Ministry of Agriculture, Irrigation and Livestock (MAIL) | [7 empty] | Name: Napoleon Navarro, Deputy Resident Representative, Programmes
Signature and Date: | Signature and Date: | [7 empty] | Signature & Date: