## Consolidated database
EUROPEAN FACILTIY FOR RURAL MARKET DEVELOPMETN (EU-FARM)
Consolidated Activities Database (April - September), 2017
[6 empty] | Completed |  | Pending |  | Cancelled
Province | Old Activity Code | New Activity Code | Component | Activity | Comments | Type of Activity | Junior SNKE (Days) |  | Senior SNKE (Days) |  | SNKE | Respective Indicator | Indicator Value |  | Measurement Unit | Proposed Date (MMM,YY) |  | Actual Date (DD,MMM,YY) |  | Province | District | Planned Participants | Actual Participants |  |  | Responsible NKE | Partner |  | Status | Remarks
[7 empty] | Planned | Actual | Planned | Actual |  |  | Planned | Achieved |  | Start | End | Start | End |  |  |  | Male | Female | Total |  | MAIL | Others
Kabul | C1.1a(a)-026-KBL | C1.1a(a)-026-KBL | 1 | Conduct PSC Meeting |  | PSC Meeting | - | - | - | - | - | 1.1a.2 | 1 | 1 | Meetings (No.) | May,17 | June,17 | 2017-05-20 | 2017-05-20 | Kabul | Center | 35 | 15 | 0 | 15 | 1 | • General Directorate for Planning and Program Coordination, Co-chair (MAIL) • General Directorate of Extension, Member (MAIL) • Directorate of private sector development ( MAIL) • ARIA (MAIL) AJ6:AK61 | • Bilateral fund management deportment/Citizen Charter, Member (MRRD) • MoCI • Directorate of Alternative Livelihood (MoCN) • Afghan Chamber of Commerce and Industries (ACCI) • General Directorate of Budget, Member (MoFA) • European Union Delegation, Member (EU Kabul Office) • NHLP, Member | Completed
Kabul | C1.1b(d)-028-KBL | C1.1b(e)-028-KBL | 1 | Organize PC Meeting in central region | Agenda developed. | PC Meeting | - | - | - | - | - | 1.1b.3 | 1 | 1 | Meetings (No.) | June,17 | June,17 | 2017-07-11 | 2017-07-11 | Kabul | Center | 20 | 15 | 1 | 16 | 2 | • PAIL Directorate | • PRRD • Citizen Charter deportment (PRRD) • Women Affair Directorate •ACCI representatives •Agriculture faculty • Other relevant projects such us (NHLP , AAIP, OFWM, Mercy Corps, SNaPP2, AAIP, CARD-F, ILO, AAEP, GFA, LML, ...) | Completed
Kabul | C1.1b(h)-029-KBL | C1.1b(f)-029-KBL | 1 | Organize 2nd PC Meeting in central region | This budget was also used for the 4th PC meeting held in Kabul on the 22nd April, 2018 | PC Meeting | - | - | - | - | - | 1.1b.3 | 1 | 1 | Meetings (No.) | Sept,17 | Sept,17 | 2017-12-25 | 2017-12-25 | Kabul | Center | 20 | 18 | 4 | 22 | 2 | • PAIL Directorate | • PRRD • Citizen Charter deportment (PRRD) • Women Affair Directorate •ACCI representatives •Agriculture faculty • Other relevant projects such us (NHLP , AAIP, OFWM, Mercy Corps, SNaPP2, AAIP, CARD-F, ILO, AAEP, GFA, LML, ...) | Completed
Balkh | C1.1b(a)-020-MZR | C3.1b(a)-020-MZR | 1 | Organize PC Meeting in Northern region (Balkh) |  | PC Meeting | - | - | - | - | - | 1.1b.3 | 1 | 1 | Meetings (No.) | May,17 | May,17 | 22/08/17 | 22/08/17 | Balkh | Center | 20 | 21 | 0 | 21 | 2 | • PAIL Directorate | • PRRD • Citizen Charter deportment (PRRD) • Women Affair Directorate •ACCI representatives •Agriculture faculty • Other relevant projects such us (NHLP , AAIP, OFWM, Mercy Corps, SNaPP2, AAIP, CARD-F, ILO, AAEP, GFA, LML, ...) | Completed
Balkh | C1.1b(b)-021-MZR | C3.1b(b)-021-MZR | 1 | Organize 2nd PC Meeting in Northern region (Balkh) | The 4th PC meeting expenditures were also charged here, due to the fact that we didn't have the approval from the EU. | PC Meeting | - | - | - | - | - | 1.1b.3 | 1 | 1 | Meetings (No.) | Augs,17 | Augs,17 | 17/12/17 | 17/12/17 | Balkh | Center | 20 | 40 | 2 | 42 | 2 | • PAIL Directorate | • PRRD • Citizen Charter deportment (PRRD) • Women Affair Directorate •ACCI representatives •Agriculture faculty • Other relevant projects such us (NHLP , AAIP, OFWM, Mercy Corps, SNaPP2, AAIP, CARD-F, ILO, AAEP, GFA, LML, ...) | Completed
Nangarhar | C1.1b(b)-017-JAA | C2.1b(a)-017-JAA | 1 | Organize PC Meeting in Eastern region (Nangarhar) |  | PC Meeting | - | - | - | - | - | 1.1b.3 | 1 | 1 | Meetings (No.) | Apri,17 | Apri,17 | 2017-08-09 | 2017-08-09 | Nangarhar | Center | 20 | 19 | 0 | 19 | 2 | • PAIL Directorate | • PRRD • Citizen Charter deportment (PRRD) • Women Affair Directorate •ACCI representatives •Agriculture faculty • Other relevant projects such us (NHLP , AAIP, OFWM, Mercy Corps, SNaPP2, AAIP, CARD-F, ILO, AAEP, GFA, LML, ...) | Completed
Nangarhar | C1.1b(f)-018-JAA | C2.1b(b)-018-JAA | 1 | Organize 2nd PC Meeting in Eastern region (Nangarhar) | 17th December, 2017 | PC Meeting | - | - | - | - | - | 1.1b.3 | 1 |  | Meetings (No.) | July,17 | July,17 | 18/12/17 | 18/12/17 | Nangarhar | Center | 20 | 21 | 0 | 21 | 2 | • PAIL Directorate | • PRRD • Citizen Charter deportment (PRRD) • Women Affair Directorate •ACCI representatives •Agriculture faculty • Other relevant projects such us (NHLP , AAIP, OFWM, Mercy Corps, SNaPP2, AAIP, CARD-F, ILO, AAEP, GFA, LML, ...) | Completed
Herat | C1.1b(a)-019-HER | C4.1b(a)-019-HER | 1 | Organize PC meeting in Western region | PC meeting in May wiill be conducted using the same budget. This PC meeting was conducted on 6May where 32 participants participated. | PC Meeting | - | - | - | - | - | 1.1b.3 | 1 | 1 | Meetings (No.) | Apri,17 | Apri,17 | 2017-06-08 | 2017-06-08 | Herat | Center | 20 | 16 | 0 | 16 | 2 | • PAIL Directorate | • PRRD • Citizen Charter deportment (PRRD) • Women Affair Directorate •ACCI representatives •Agriculture faculty • Other relevant projects such us (NHLP , AAIP, OFWM, Mercy Corps, SNaPP2, AAIP, CARD-F, ILO, AAEP, GFA, LML, ...) | Completed
Herat | C1.1b(b)-020-HER | C4.1b(b)-020-HER | 1 | Organize 2nd PC meeting in Western region | Visit of Hamdard sahib and Merchant charges ( May, 18) charged to this activity | PC Meeting | - | - | - | - | - | 1.1b.3 | 1 |  | Meetings (No.) | July,17 | July,17 | 2018-07-01 | 2018-07-01 | Herat | Center | 20 |  |  |  | 2 | • PAIL Directorate | • PRRD • Citizen Charter deportment (PRRD) • Women Affair Directorate •ACCI representatives •Agriculture faculty • Other relevant projects such us (NHLP , AAIP, OFWM, Mercy Corps, SNaPP2, AAIP, CARD-F, ILO, AAEP, GFA, LML, ...) | Completed
Herat | C1.1b(c)-021-HER | C4.1b(c)-021-HER | 1 | Organize PC facilitation visit to Western region (Herat) |  | Visit | - | - | - | - | - | 1.1b.3.1 | 1 | 1 | Visits (No) | Apri,17 | Apri,17 | 2017-08-05 | 2017-08-05 | Herat | Center | 2 | 1 | 0 | 1 | 2 | NA | NA | Completed
Nangarhar | C1.1b(j)-019-JAA | C2.1b(c)-019-JAA | 1 | Organize PC facilitation visit to Eastern region (Nangarhar) |  | Visit | - | - | - | - | - | 1.1b.3.1 | 1 | 1 | Visits (No) | Apri,17 | Apri,17 | 2017-08-09 | 2017-08-09 | Nangarhar | Center | 2 | 1 | 0 | 1 | 2 | NA | NA | Completed
Balkh | C1.1b(c)-022-MZR | C3.1b(c)-022-MZR | 1 | Organize PC facilitation visit to Northern region (Balkh) | The 4th PC meeting expenditures were also charged here, due to the fact that we didn't have the approval from the EU. | Visit | - | - | - | - | - | 1.1b.3.1 | 1 |  | Visits (No) | May,17 | May,17 | 21/08/17 | 21/08/17 | Balkh | Center | 2 | 1 | 0 | 1 | 2 | NA | NA | Completed
Herat | C1.1b(d)-022-HER | C4.1b(d)-022-HER | 1 | Organize 2nd PC facilitation visit to Western region (Herat) |  | Visit | - | - | - | - | - | 1.1b.3.1 | 1 | 1 | Visits (No) | July,17 | July,17 | 2018-07-01 | 2018-07-01 | Herat | Center | 2 | 2 | 1 | 3 | 2 | NA | NA | Completed
Nangarhar | C1.1b(m)-020-JAA | C2.1b(d)-020-JAA | 1 | Organize 2nd PC facilitation visit to Eastern region (Nangarhar) |  | Visit | - | - | - | - | - | 1.1b.3.1 | 1 | 1 | Visits (No) | Apri,17 | Apri,17 | 16/12/17 | 16/12/17 | Nangarhar | Center | 2 |  |  |  | 2 | NA | NA | Completed
Balkh | C1.1b(n)-023-MZR | C3.1b(d)-023-MZR | 1 | Organize 2nd PC facilitation visit to Northern region (Balkh) |  | Visit | - | - | - | - | - | 1.1b.3.1 | 1 |  | Visits (No) | Augs,17 | Augs,17 | 16/12/17 | 16/12/17 | Balkh | Center | 2 | 1 | 0 | 1 | 2 | NA | NA | Completed
Nangarhar | C1.2a(b)-025-JAA | C2.2a(a)-025-JAA | 1 | Organize workshop for introducing FLRC,E-Ex in Eastern region (Nangarhar) | The workshp was conducted by the SNaPP2, only eastern region team helped the the team in organization of the visit. | Workshop | - | - | - | - | - | 1.2a.2 | 1 | 1 | Workshops (No.) | June,17 | July,17 | 2017-08-21 | 2017-08-21 | Nangarhar | Center | 40 |  |  |  | 1 | • PAIL | • PRRD • Citizen Charter (PRRD) • MoCI • Women Affaires deportment • Afghan Chamber of Commerce and Industries (ACCI) • NHLP •Agriculture faculty • Other relevant projects such us (NHLP , AAIP, OFWM, Mercy Corps, SNaPP2, AAIP, CARD-F, ILO, AAEP, GFA, LML, FAO, ...) | Completed
Balkh | C1.2a(c)-028-MZR | C3.2a(a)-028-MZR | 1 | Organize workshop for introducing FLRC,E-Ex in Northern region (Balkh) | Conducted by ONFWM. Wadan Addended this | Workshop | - | - | - | - | - | 1.2a.2 | 1 | 1 | Workshops (No.) | June,17 | July,17 | 20/09/17 | 20/09/17 | Balkh | Center | 4 |  |  |  | 1 | • PAIL | • PRRD • Citizen Charter (PRRD) • MoCI • Women Affaires deportment • Afghan Chamber of Commerce and Industries (ACCI) • NHLP •Agriculture faculty • Other relevant projects such us (NHLP , AAIP, OFWM, Mercy Corps, SNaPP2, AAIP, CARD-F, ILO, AAEP, GFA, LML, FAO, ...) | Completed
Herat | C1.2a(d)-027-HER | C4.2a(a)-027-HER | 1 | Organize workshop for introducing FLRC,E-Ex in Western region (Herat) |  | Workshop | - | - | - | - | - | 1.2a.2 | 1 | 1 | Workshops (No.) | June,17 | July,17 | 2017-12-12 | 2017-12-12 | Herat | Center | 40 | 95 | 3 | 98 | 1 | • PAIL | • PRRD • Citizen Charter (PRRD) • MoCI • Women Affaires deportment • Afghan Chamber of Commerce and Industries (ACCI) • NHLP •Agriculture faculty • Other relevant projects such us (NHLP , AAIP, OFWM, Mercy Corps, SNaPP2, AAIP, CARD-F, ILO, AAEP, GFA, LML, FAO, ...) | Completed
Kabul | C1.2a(e)-033-KBL | C1.2a(e)-033-KBL | 1 | Organize workshop for introducing FLRC,E-Ex in Central region (Kabul) |  | Workshop | - | - | - | - | - | 1.2a.2 | 1 | 1 | Workshops (No.) | June,17 | July,17 | 26/7/17 | 26/7/17 | Kabul | Center | 40 |  |  |  | 1 | • General Directorate for Planning and Program Coordination (MAIL) • General Directorate of Extension, Member (MAIL) • Directorate of private sector development ( MAIL) • ARIA (MAIL) • PAIL Directors | • MRRD • Citizen Charter (MRRD) • MoCI • Women Affaires deportment • Afghan Chamber of Commerce and Industries (ACCI) • NHLP •Agriculture faculty • Other relevant projects such us (NHLP , AAIP, OFWM, Mercy Corps, SNaPP2, AAIP, CARD-F, ILO, AAEP, GFA, LML, FAO, ...) | Completed
Nangarhar | C1.5b(c)-029-JAA | C2.5b(c)-029-JAA | 1 | Conduct workshop in Eastern region existing communication channels between MAIL & MRRD | Workshop | 8000 | - | - | - | - | 1.5b.1 | 1 |  | Workshops (No.) | Sept,17 | Sept,17 |  |  | Nangarhar | Center | 30 |  |  |  | 3 | • PAIL Directorates | • PRRD • Citizen Charter Program (PRRD) • NHLP • Other involved projects in implementation of cross ministerial projects. • • | Pending
Nangarhar | C3.3b(a)-031-JAA | C6.3b(a)-031-JAA | 3 | Post-harvest training to farmers on onion value chain | Dec | Training |  | - | - | - | - | 3.3b.1 | 1 |  | Trainings (No.) | Apri,17 | Sept,17 | 25/12/17 | 25/12/17 | Nangarhar | Kama | 15 | 10 | 0 | 10 | 5 | • DAIL Directorate of Nangarhar and related deparment | • NHLP • PRRD social orgnizer • Nangarhar Fruit and vegetable wholesalar association | Completed
Nangarhar | C3.3b(b)-032-JAA | C6.3b(b)-032-JAA | 3 | Post-harvest training to farmers on onion value chain | Dec | Training |  | - | - | - | - | 3.3b.1 | 1 |  | Trainings (No.) | Apri,17 | Sept,17 | 26/12/17 | 26/12/17 | Nangarhar | Goashta | 15 | 10 | 0 | 10 | 5 | • DAIL Directorate of Nangarhar and related deparment | • NHLP • PRRD social orgnizer • Nangarhar Fruit and vegetable wholesalar association | Completed
Nangarhar | C3.3b(c)-033-JAA | C6.3b(c)-033-JAA | 3 | Post-harvest training to farmers on onion value chain | Dec | Training |  | - | - | - | - | 3.3b.1 | 1 |  | Trainings (No.) | Apri,17 | Sept,17 | 27/12/17 | 27/12/17 | Nangarhar | Kuz Kunar | 15 | 10 | 0 | 10 | 5 | • DAIL Directorate of Nangarhar and related deparment | • NHLP • PRRD social orgnizer • Nangarhar Fruit and vegetable wholesalar association | Completed
Nangarhar | C3.3b(d)-034-JAA | C6.3b(d)-034-JAA | 3 | Post-harvest training to farmers on onion value chain | Dec | Training |  | - | - | - | - | 3.3b.1 | 1 | 1 | Trainings (No.) | Apri,17 | Sept,17 | 2018-01-01 | 2018-01-01 | Nangarhar | Surkhroad | 15 | 10 | 0 | 10 | 5 | • DAIL Directorate of Nangarhar and related deparment | • NHLP • PRRD social orgnizer • Nangarhar Fruit and vegetable wholesalar associati | Completed
Nangarhar | C3.3b(e)-035-JAA | C6.3b(e)-035-JAA | 3 | Post-harvest training to farmers on onion value chain - food processing |  | Training |  | - | - | - | - | 3.3b.1 | 1 | 1 | Trainings (No.) | Apri,17 | Sept,17 | 2017-10-07 | 2017-10-07 | Nangarhar | Kuz Kunar | 15 | 1 | 30 | 31 | 5 | • DAIL Directorate of Nangarhar and related deparment | • NHLP • PRRD social orgnizer • Nangarhar Fruit and vegetable wholesalar associati | Completed
Nangarhar | C3.3b(f)-036-JAA | C6.3b(f)-036-JAA | 3 | Technical training to farmers in beekeeping value chain |  | Training |  | - | - | - | - | 3.3b.1 | 1 | 1 | Trainings (No.) | Apri,17 | Sept,17 | 2017-10-25 | 2017-10-25 | Nangarhar | Kuz Kunar | 15 | 0 | 18 | 18 | 5 | • DAIL Directorate of Nangarhar and related deparment | • NHLP • PRRD social orgnizer • Nangarhar Fruit and vegetable wholesalar associatir | Completed
Nangarhar | C3.3b(g)-037-JAA | C6.3b(g)-037-JAA | 3 | Technical training to farmers in beekeeping value chain |  | Training |  | - | - | - | - | 3.3b.1 | 1 | 1 | Trainings (No.) | Apri,17 | Sept,17 | 2017-10-30 | 2017-10-30 | Nangarhar | Center | 15 | 0 | 21 | 21 | 5 | • DAIL Directorate of Nangarhar and related deparment | • NHLP • PRRD social orgnizer • Nangarhar Fruit and vegetable wholesalar association | Completed | Planning costs charged.
Nangarhar | C3.3b(h)-038-JAA | C6.3b(h)-038-JAA | 3 | Technical training to farmers in beekeeping value chain - food processing | Food Processing | Training |  | - | - | - | - | 3.3b.1 | 1 | 1 | Trainings (No.) | Apri,17 | Sept,17 | 2017-10-08 | 2017-10-08 | Nangarhar | Center | 15 | 0 | 20 | 20 | 5 | • DAIL Directorate of Nangarhar and related deparment | • NHLP • PRRD social orgnizer • NBA Nangarhar Beekeeping association | Completed
Nangarhar | C3.3b(i)-039-JAA | C6.3b(i)-039-JAA | 3 | Technical training to farmers in beekeeping value chain - 2nd workshop |  | Training |  | - | - | - | - | 3.3b.1 | 1 |  | Trainings (No.) | Apri,17 | Sept,17 | 2017-11-13 | 2017-11-13 | Nangarhar | Center | 15 |  |  |  | 5 | • DAIL Directorate of Nangarhar and related deparment | • NHLP • PRRD social orgnizer • NBA Nangarhar Beekeeping association | Completed
Nangarhar | C3.3b(j)-040-JAA | C6.3b(j)-040-JAA | 3 | Technical training to farmers in beekeeping value chain | Jan | Training |  | - | - | - | - | 3.3b.1 | 1 |  | Trainings (No.) | Apri,17 | Sept,17 | 2018-04-02 | 2018-04-02 | Nangarhar | Center | 15 | 19 | 0 | 19 | 5 | • DAIL Directorate of Nangarhar and related deparment | • NHLP • PRRD social orgnizer • NBA Nangarhar Beekeeping association | Completed
Nangarhar | C3.3b(k)-041-JAA | C6.3b(k)-041-JAA | 3 | Technical training to farmers in beekeeping value chain | Jan | Training |  | - | - | - | - | 3.3b.1 | 1 | 1 | Trainings (No.) | Apri,17 | Sept,17 | 2018-12-02 | 2018-12-02 | Nangarhar | Center | 15 | 20 | 0 | 20 | 5 | • DAIL Directorate of Nangarhar and related deparment | • NHLP • PRRD social orgnizer • NBA Nangarhar Beekeeping association | Completed
Nangarhar | C3.3b(l)-042-JAA | C6.3b(l)-042-JAA | 3 | Technical training to farmers in beekeeping value chain (Food Processing Evaluation ) |  | Training |  | - | - | - | - | 3.3b.1 | 1 | 1 | Trainings (No.) | Apri,17 | Sept,17 | 2017-11-12 | 2017-11-12 | Nangarhar | Center | 15 | 0 | 22 | 22 | 5 | • DAIL Directorate of Nangarhar and related deparment | • NHLP • PRRD social orgnizer • NBA Nangarhar Beekeeping association | Completed
Nangarhar | C3.2a(a)-048-JAA | C6.2a(a)-048-JAA | 3 | Consultation workshop stakeholder in Honey VC |  | Workshop |  |  | - | - |  | 3.2a.1 | 1 | 1 | Workshops (No.) | Apri,17 | Sept,17 | 2017-02-08 | 2017-02-08 | Nangarhar | Center | 15 | 23 | 0 | 23 | 5 | • DAIL Directorate of Nangarhar and related deparment | • NHLP • NBA | Completed
Nangarhar | C3.2a(b)-049-JAA | C6.2a(b)-049-JAA | 3 | Consultation workshop stakeholder in Onion VC |  | Workshop |  |  | - | - |  | 3.2a.1 | 1 | 1 | Workshops (No.) | Apri,17 | Sept,17 | 2017-07-31 | 2017-07-31 | Nangarhar | Center | 15 | 19 | 0 | 19 | 5 | • DAIL Directorate of Nangarhar and related deparment | • NHLP • Traders | Completed
Nangarhar | C3.3f(a)-051-JAA | C6.3f(a)-051-JAA | 3 | Conduct workshop for identifying gaps in agr.inputs | Technical training in Onion VC | Workshop |  |  | - | - |  | 3.3.f.3 | 1 | 1 | Workshops (No.) | Apri,17 | Sept,17 | 2018-03-01 | 2018-03-01 | Nangarhar | Rodat (Darbazar) | 15 | 10 | 0 | 10 | 5 | • DAIL Directorate of Nangarhar and related deparment | • NHLP • processers and traders • Lead farmer | Completed
Nangarhar | C3.3f(b)-052-JAA | C6.3f(b)-052-JAA | 3 | Conduct workshop for identifying gaps in agr.inputs | Honey VC Jan | Workshop |  |  | - | - |  | 3.3.f.3 | 1 |  | Workshops (No.) | Apri,17 | Sept,17 | 14/02/18 | 14/02/18 | Nangarhar | Center | 15 |  |  |  | 5 | • DAIL Directorate of Nangarhar and related deparment | • NHLP • processers and traders • Lead farmer | Completed
Nangarhar | C3.1c(a)-053-JAA | C6.1c(a)-053-JAA | 3 | Workshop on ISO Standards | Participants list is prepared | Workshop |  |  | - | - |  | 3.1c.2 | 1 | 1 | Workshops (No.) | Apri,17 | Sept,17 | 2017-11-12 | 2017-11-12 | Nangarhar | Center | 15 | 19 | 8 | 27 | 5 | • DAIL Directorate of Nangarhar and related deparment | • NHLP • food processers and traders • Producer | Completed
Kabul | C3.1c(a)-044-KBL | C5.1c(a)-044-KBL | 3 | Workshop on ISO Standards |  | Workshop |  |  | - | - |  | 3.1c.2 | 1 | 1 | Workshops (No.) | Apri,17 | Sept,17 | 23/01/2018 | 23/01/2018 | Kabul | Center | 40 | 33 | 5 | 38 | 6 | MAIL, DAIL | NHLP, Traders, Associations, RADP-S | Completed
Kabul | C3.2a(a)-045-KBL | C5.2a(a)-045-KBL | 3 | VC Consultation workshop with different stakeholder - Food processing women |  | Workshop |  |  | - | - |  | 3.2a.1 | 1 | 1 | Workshops (No.) | Apri,17 | Sept,17 | 25/7/17 | 25/7/17 | Kabul | Center | 20 | 16 | 0 | 19 | 6 | MAIL, DAIL | NHLP, Traders, Associations, RADP-S | Completed
Kabul | C3.2a(b)-046-KBL | C5.2a(b)-046-KBL | 3 | VC Consultation workshop with different stakeholder (Grapes & Apple Value Chains) | Grapes & Apple both consultation workshpos were conducted in this one workshop | Workshop |  |  | - | - |  | 3.2a.1 | 1 | 1 | Workshops (No.) | Apri,17 | Sept,17 | 2017-05-08 | 2017-05-08 | Kabul | Center | 20 | 13 | 0 | 13 | 6 | MAIL, DAIL | NHLP, Traders, Associations, RADP-S | Completed
Kabul | C3.2a(c)-047-KBL | C5.2a(c)-047-KBL | 3 | VC Consultation workshop with different stakeholder - Apple |  | Workshop |  |  | - | - |  | 3.2a.1 | 1 |  | Workshops (No.) | Apri,17 | Sept,17 | 27/9/17 | 27/9/17 | Kabul | Center | 20 | 18 | 0 | 18 | 6 | MAIL, DAIL | NHLP, Traders, Associations, RADP-S | Completed
Kabul | C3.2a(d)-048-KBL | C5.2a(d)-048-KBL | 3 | VC Consultation workshop with different stakeholder | Private Sector - Fresh fruit association | Workshop |  |  | - | - |  | 3.2a.1 | 1 |  | Workshops (No.) | Apri,17 | Sept,17 | 13/12/17 | 13/12/17 | Kabul | Center | 20 | 25 | 0 | 25 | 6 | MAIL, DAIL | NHLP, Traders, Associations, RADP-S | Completed
Kabul | C3.2a(e)-049-KBL | C5.2a(e)-049-KBL | 3 | VC Consultation workshop with different stakeholder | Women workshop for creating different groups/assocation | Workshop |  |  | - | - |  | 3.2a.1 | 1 |  | Workshops (No.) | Apri,17 | Sept,17 | 2018-03-04 | 2018-03-04 | Kabul | Center | 20 |  |  |  | 6 | MAIL, DAIL | NHLP, Traders, Associations, RADP-S | Completed
Kabul | C3.2a(f)-050-KBL | C5.2a(f)-050-KBL | 3 | VC Consultation workshop with different stakeholder | VC Consultation workshop in mulbery in Panjshir | Workshop |  |  | - | - |  | 3.2a.1 | 1 |  | Workshops (No.) | Apri,17 | Sept,17 | 24/04/18 | 24/04/18 | Kabul | Center | 20 |  |  |  | 6 | MAIL, DAIL | NHLP, Traders, Associations, RADP-S | Completed
Kabul | C3.3b(b)-052-KBL | C5.3b(d)-052-KBL | 3 | Technical training to farmers in selected VCs - Grapes VC | Trainners and Trainees are identified. Plan for conducting training is done | Training |  | - | - | - | - | 3.3b.1 | 1 |  | Trainings (No.) | Apri,17 | Sept,17 | 28/08/17 | 28/08/17 | Kabul | Center | 15 | 19 | 0 | 19 | 6 | MAIL, DAIL | NHLP, Traders, Associations, RADP-S | Completed | Grapes Harvesting Training
Kabul | C3.3b(c)-053-KBL | C5.3b(e)-053-KBL | 3 | Technical training to farmers in selected VCs - Food Processing | Trainners and Trainees are identified. Plan for conducting training is done | Training |  | - | - | - | - | 3.3b.1 | 1 |  | Trainings (No.) | Apri,17 | Sept,17 | 16/09/17 | 17/09/17 | Kabul | Center | 15 | 0 | 24 | 24 | 6 | MAIL, DAIL | NHLP, Traders, Associations, RADP-S | Completed | Fodd processing training for women
Kabul | C3.3b(d)-054-KBL | C5.3b(f)-054-KBL | 3 | Technical training to farmers in selected VCs - Food Processing | Trainners and Trainees are identified. Plan for conducting training is done | Training |  | - | - | - | - | 3.3b.1 | 1 |  | Trainings (No.) | Apri,17 | Sept,17 | 18/09/17 | 19/09/17 | Kabul | Center | 15 | 53 and 54 activities codes were used for one activity |  |  | 6 | MAIL, DAIL | NHLP, Traders, Associations, RADP-S | Completed | Fodd processing training for women
Kabul | C3.3b(e)-055-KBL | C5.3b(g)-055-KBL | 3 | Technical training to farmers in selected VCs -Apple VC |  | Training |  | - | - | - | - | 3.3b.1 | 1 |  | Trainings (No.) | Apri,17 | Sept,17 | 2017-10-10 | 2017-10-10 | Kabul | Center | 15 | 44 | 0 | 44 | 6 | MAIL, DAIL | NHLP, Traders, Associations, RADP-S | Completed
Kabul | C3.3b(f)-056-KBL | C5.3b(h)-056-KBL | 3 | Technical training to farmers in selected VCs - Food Processing |  | Training |  | - | - | - | - | 3.3b.1 | 1 |  | Trainings (No.) | Apri,17 | Sept,17 | 23/10/2017 | 23/10/17 | Kabul | Center | 15 | 21 | 0 | 21 | 6 | MAIL, DAIL | NHLP, Traders, Associations, RADP-S | Completed
Kabul | C3.3b(g)-057-KBL | C5.3b(i)-057-KBL | 3 | Technical training to farmers in selected VCs - Food Processing |  | Training |  | - | - | - | - | 3.3b.1 | 1 |  | Trainings (No.) | Apri,17 | Sept,17 | 24/10/17 | 25/10/17 | Kabul | Center | 15 | same as reported in activity 056 |  |  | 6 | MAIL, DAIL | NHLP, Traders, Associations, RADP-S | Completed
Kabul | C3.3b(h)-058-KBL | C5.3b(j)-058-KBL | 3 | Technical training to farmers in selected VCs - Apple VC |  | Training |  | - | - | - | - | 3.3b.1 | 1 |  | Trainings (No.) | Apri,17 | Sept,17 | 2017-10-10 | 2017-10-10 | Kabul | Center | 15 | 42 | 0 | 42 | 6 | MAIL, DAIL | NHLP, Traders, Associations, RADP-S | Completed
Kabul | C3.3b(i)-059-KBL | C5.3b(k)-059-KBL | 3 | Technical training to farmers in selected VCs - Food Processing |  | Training |  | - | - | - | - | 3.3b.1 | 1 |  | Trainings (No.) | Apri,17 | Sept,17 | 6//11/2017 | 2017-08-11 | Kabul | Center | 15 | 0 | 26 | 0 | 6 | MAIL, DAIL | NHLP, Traders, Associations, RADP-S | Completed
Kabul | C3.3b(j)-060-KBL | C5.3b(l)-060-KBL | 3 | Technical training to farmers in selected VCs - Food Processing |  | Training |  | - | - | - | - | 3.3b.1 | 1 |  | Trainings (No.) | Apri,17 | Sept,17 |  |  | Kabul | Center | 15 | 59 & 60 activities codes were used for one activity. |  |  | 6 | MAIL, DAIL | NHLP, Traders, Associations, RADP-S | Completed
Kabul | C3.3b(h)-061-KBL | C5.3b(m)-061-KBL | 3 | Technical training to farmers in selected VCs - Evaluation of food processing training |  | Training |  | - | - | - | - | 3.3b.1 | 1 | 1 | Trainings (No.) | Apri,17 | Sept,17 | 27/11/17 | 28/11/17 | Kabul | Center | 15 | 0 | 33 | 33 | 6 | MAIL, DAIL | NHLP, Traders, Associations, RADP-S | Completed
Kabul | C3.3b(i)-062-KBL | C5.3b(n)-062-KBL | 3 | Technical training to farmers in selected VCs - Women simple accounting | 16 and 17 dec | Training |  | - | - | - | - | 3.3b.1 | 1 |  | Trainings (No.) | Apri,17 | Sept,17 | 16/12/17 | 17/12/17 | Kabul | Center | 15 | 0 | 41 | 41 | 6 | MAIL, DAIL | NHLP, Traders, Associations, RADP-S | Completed
Kabul | C3.3b(j)-063-KBL | C5.3b(o)-063-KBL | 3 | Technical training to farmers in selected VCs - Apple VC | Book keeping training to women food processing & inputs distribution | Training |  | - | - | - | - | 3.3b.1 | 1 |  | Trainings (No.) | Apri,17 | Sept,17 | 26/12/17 | and 31/12/17 | Kabul | Center | 15 |  |  |  | 6 | MAIL, DAIL | NHLP, Traders, Associations, RADP-S | Completed
Kabul | C3.3b(k)-064-KBL | C5.3b(p)-064-KBL | 3 | Technical training to farmers in selected VCs | Practical training in Book keeping to women food processors and association members. (4 days) 3 days TOT to 9 NHLP extention worker in accounting and 1 day was allocated for creating women food processing association. | Training |  | - | - | - | - | 3.3b.1 | 1 | 1 | Trainings (No.) | Apri,17 | Sept,17 | 25/3/18 | 25/3/18 | Kabul | Center | 15 | 0 | 9 | 8 | 6 | MAIL, DAIL | NHLP, Traders, Associations, RADP-S | Completed
Kabul | C3.3b(l)-065-KBL | C5.3b(q)-065-KBL | 3 | Technical training to farmers in selected VCs | Kapisa - Mulbury training | Training |  | - | - | - | - | 3.3b.1 | 1 |  | Trainings (No.) | Apri,17 | Sept,17 |  |  | Kabul | Center | 15 |  |  |  | 6 | MAIL, DAIL | NHLP, Traders, Associations, RADP-S | Completed
Kabul | C3.3c(a)-066-KBL | C5.3c(b)-066-KBL | 3 | Exposure visit to Tajikistan | Beside Tajikistan Exposure visit. On 18 November, 2018 Around 65 different stakeholders including, farmers from leading Grape producing districts of Herat province, Head of PAIL’s extension department, head of Urdokhan Research farm, Regional marketing manager of NHLP, ICARDA Provincial manager and EU-FARM staff participated in the event on follow up on exposure visit of Tajikistan and Kandahar on Grape VC. | Visit |  | - | - | - | - | 3.3c.1 | 1 |  | Visits (No) | Apri,17 | Sept,17 | 25/11/17 | 30/11/17 | Kabul | Center | 8 | 10 | 0 | 10 | 6 | MAIL, DAIL | NHLP, Traders, Associations, RADP-S | Completed
Kabul | C3.3f(a)-067-KBL | C5.3f(a)-067-KBL | 3 | Workshop for identification of input supplies challenges | Discussion with partners (AAIP, private sector & extension is going on) | Workshop |  |  | - | - | - | 3.3.f.3 | 1 | 1 | Workshops (No.) | Apri,17 | Sept,17 | 2017-08-20 | 2017-08-20 | Kabul | Center | 15 | 75 | 0 | 75 | 6 | MAIL, DAIL | NHLP, Traders, Associations, RADP-S | Completed | Legislation Workshop
Kabul | C3.3f(b)-068-KBL | C5.3f(b)-068-KBL | 3 | Workshop for identification of input supplies challenges - |  | Workshop |  |  | - | - | - | 3.3.f.3 | 1 |  | Workshops (No.) | Apri,17 | Sept,17 | 2017-10-07 | 2017-10-07 | Kabul | Center | 15 | 30 | 0 | 30 | 6 | MAIL, DAIL | NHLP, Traders, Associations, RADP-S | Completed
Herat | C3.3b(a)-032-HER | C8.3b(a)-032-HER | 3 | Technical training to farmers in selected VCs - grapes VC | Workshop for geeting feedback regarding the Kandahar exposure visits. | Training |  | - | - | - | - | 3.3b.1 | 1 | 1 | Trainings (No.) | Apri,17 | Sept,17 | 28/08/17 | 28/08/17 | Herat | Guzara | 15 | 43 | 0 | 43 | 4 | . PAIL Department | . Farmers and Gardeners | Completed
Herat | C3.3b(b)-033-HER | C8.3b(b)-033-HER | 3 | Technical training to farmers in selected VCs - Saffron |  | Training |  | - | - | - | - | 3.3b.1 | 1 | 1 | Trainings (No.) | Apri,17 | Sept,17 | 2017-10-10 | 2017-10-10 | Herat | Guzara | 15 | 0 | 43 | 43 | 4 | . PAIL Department | . Farmers and Gardeners | Completed
Herat | C3.3b(c)-034-HER | C8.3b(c)-034-HER | 3 | Technical training to farmers in selected VCs - Saffron |  | Training |  | - | - | - | - | 3.3b.1 | 1 | 1 | Trainings (No.) | Apri,17 | Sept,17 | 2017-10-11 | 2017-10-11 | Herat | Guzara | 15 | 42 | 0 | 42 | 4 | . PAIL Department | . Farmers and Gardeners | Completed
Herat | C3.3b(d)-035-HER | C8.3b(d)-035-HER | 3 | Technical training to farmers in selected VCs - Saffron |  | Training |  | - | - | - | - | 3.3b.1 | 1 | 1 | Trainings (No.) | Apri,17 | Sept,17 | 2017-10-15 | 2017-10-15 | Herat | Injil | 15 | 48 | 0 | 48 | 4 | . PAIL Department | . Farmers and Gardeners | Completed
Herat | C3.3b(e)-036-HER | C8.3b(e)-036-HER | 3 | Technical training to farmers in selected VCs - Saffron Female |  | Training |  | - | - | - | - | 3.3b.1 | 1 | 1 | Trainings (No.) | Apri,17 | Sept,17 | 16/10/17 | 16/10/17 | Herat | Injil | 15 | 43 | 0 | 43 | 4 | . PAIL Department | . Farmers and Gardeners | Completed
Herat | C3.3b(f)-037-HER | C8.3b(f)-037-HER | 3 | Technical training to farmers in selected VCs - Saffron Female |  | Training |  | - | - | - | - | 3.3b.1 | 1 | 1 | Trainings (No.) | Apri,17 | Sept,17 | 2017-10-14 | 2017-10-14 | Herat | Zenda Jan | 15 | 37 | 6 | 43 | 4 | . PAIL Department | . Farmers and Gardeners | Completed
Herat | C3.3b(g)-038-HER | C8.3b(g)-038-HER | 3 | Technical training to farmers in selected VCs - saffron | 38 & 39 one training - Saffron | Training |  | - | - | - | - | 3.3b.1 | 1 | 1 | Trainings (No.) | Apri,17 | Sept,17 | 2017-11-04 | 2017-11-04 | Herat | Guzara | 15 | 0 | 30 | 30 | 4 | . PAIL Department | . Farmers and Gardeners | Completed
Herat | C3.3b(h)-039-HER | C8.3b(h)-039-HER | 3 | Technical training to farmers in selected VCs - saffron |  | Training |  | - | - | - | - | 3.3b.1 | 1 | 1 | Trainings (No.) | Apri,17 | Sept,17 | 2017-11-04 | 2017-11-04 | Herat | Guzara | 15 | 0 | 0 | Activity 38 | 4 | . PAIL Department | . Farmers and Gardeners | Completed
Herat | C3.3b(i)-040-HER | C8.3b(i)-040-HER | 3 | Technical training to farmers in selected VCs | 40 & 41 one training - Saffron | Training |  | - | - | - | - | 3.3b.1 | 1 | 1 | Trainings (No.) | Apri,17 | Sept,17 | 2017-11-05 | 2017-11-05 | Herat | Guzara | 15 | 0 | 30 | 30 | 4 | . PAIL Department | . Farmers and Gardeners | Completed
Herat | C3.3b(j)-041-HER | C8.3b(j)-041-HER | 3 | Technical training to farmers in selected VCs |  | Training |  | - | - | - | - | 3.3b.1 | 1 | 1 | Trainings (No.) | Apri,17 | Sept,17 | 40 & 41 was one activity |  | Herat | Injil | 15 | 40 & 41 was one activity |  |  | 4 | . PAIL Department | . Farmers and Gardeners | Completed
Herat | C3.3b(k)-042-HER | C8.3b(k)-042-HER | 3 | Technical training to farmers in selected VCs |  | Training |  | - | - | - | - | 3.3b.1 | 1 | 1 | Trainings (No.) | Apri,17 | Sept,17 | 2017-11-06 | 2017-11-06 | Herat | Injil | 15 | 0 | 30 | 0 | 4 | . PAIL Department | . Farmers and Gardeners | Completed
Herat | C3.3b(l)-043-HER | C8.3b(l)-043-HER | 3 | Technical training to farmers in selected VCs | 42&43 one training due to unavailbility of funds - Saffon | Training |  | - | - | - | - | 3.3b.1 | 1 | 1 | Trainings (No.) | Apri,17 | Sept,17 | 42&43 one training due to unavailbility of funds - Saffon |  | Herat | Injil | 15 | 42&43 one training due to unavailbility of funds - Saffon |  |  | 4 | . PAIL Department | . Farmers and Gardeners | Completed
Herat | C3.3b(m)-044-HER | C8.3b(m)-044-HER | 3 | Technical training to farmers in selected VCs - Food Processing | Food Processing | Training |  | - | - | - | - | 3.3b.1 | 1 | 1 | Trainings (No.) | Apri,17 | Sept,17 | 2017-10-30 | 2017-10-30 | Herat | Zenda Jan | 15 | 0 | 32 | 0 | 4 | . PAIL Department | . Farmers and Gardeners | Completed
Herat | C3.3b(n)-045-HER | C8.3b(n)-045-HER | 3 | Technical training to farmers in selected VCs - Food Processing | Food Processing | Training |  | - | - | - | - | 3.3b.1 | 1 | 1 | Trainings (No.) | Apri,17 | Sept,17 | 2017-10-31 | 2017-10-31 | Herat | Zenda Jan | 15 | 44 & 45 were conducted together |  |  | 4 | . PAIL Department | . Farmers and Gardeners | Completed
Herat | C3.3b(o)-046-HER | C8.3b(o)-046-HER | 3 | Technical training to farmers in selected VCs - Food Processing | Food Processing | Training |  | - | - | - | - | 3.3b.1 | 1 | 1 | Trainings (No.) | Apri,17 | Sept,17 | 2017-11-01 | 2017-11-01 | Herat | Zenda Jan | 15 | 0 | 40 | 40 | 4 | . PAIL Department | . Farmers and Gardeners | Completed
Herat | C3.3b(p)-047-HER | C8.3b(p)-047-HER | 3 | Technical training to farmers in selected VCs - Food Processing | Food Processing | Training |  | - | - | - | - | 3.3b.1 | 1 | 1 | Trainings (No.) | Apri,17 | Sept,17 | 2017-11-02 | 2017-11-02 | Herat | Injil | 15 | 46 & 47 were conducted together |  |  | 4 | . PAIL Department | . Farmers and Gardeners | Completed
Herat | C3.3b(q)-048-HER | C8.3b(q)-048-HER | 3 | Technical training to farmers in selected VCs | Evaluation - Food Processing | Training |  | - | - | - | - | 3.3b.1 | 1 | 1 | Trainings (No.) | Apri,17 | Sept,17 | 14/01/28 | 14/01/28 | Herat | Injil | 15 | 0 | 33 | 33 | 4 | . PAIL Department | . Farmers and Gardeners | Completed
Herat | C3.3b(r)-049-HER | C8.3b(r)-049-HER | 3 | Technical training to farmers in selected VCs | Evaluation - Food Processing | Training |  | - | - | - | - | 3.3b.1 | 1 | 1 | Trainings (No.) | Apri,17 | Sept,17 | 15/01/28 | 15/01/28 | Herat | Zenda Jan | 15 | 48 & 49 activities codes are used for one activity |  |  | 4 | . PAIL Department | . Farmers and Gardeners | Completed
Herat | C3.3b(s)-050-HER | C8.3b(s)-050-HER | 3 | Technical training to farmers in selected VCs | Female- Book keeping | Training |  | - | - | - | - | 3.3b.1 | 1 | 1 | Trainings (No.) | Apri,17 | Sept,17 | 16/01/28 | 16/01/28 | Herat | Guzara | 15 | 0 | 34 | 34 | 4 | . PAIL Department | . Farmers and Gardeners | Completed
Herat | C3.3b(t)-051-HER | C8.3b(t)-051-HER | 3 | Technical training to farmers in selected VCs | Female- Book keeping | Training |  | - | - | - | - | 3.3b.1 | 1 | 1 | Trainings (No.) | Apri,17 | Sept,17 | 17/01/28 | 17/01/28 | Herat | Guzara | 15 | 50 & 51 activities codes were used for one activity |  |  | 4 | . PAIL Department | . Farmers and Gardeners | Completed
Herat | C8.1c(a)-052-HER | C8.1c(a)-052-HER | 3 | Workshop on ISO Standards |  | Workshop |  | - | - | - |  | 3.1c.2 | 1 | 1 | Workshops (No.) | Apri,17 | Sept,17 | 2018-11-01 | 2018-11-01 | Herat | Center | 50 | 50 | 2 | 52 | 4 | . PAIL private sector department | . Farmers, Private sector, NHLP and SNaPP2 | Completed
Herat | C3.3c(a)-053-HER | C8.3c(a)-053-HER | 3 | Exposure visit to Nangarhar Fishery | Participants list is prepared | Visit |  | - | - | - | - | 3.3c.1 | 1 | 1 | Visits (No) | Apri,17 | Sept,17 | 27/8/17 | 29/8/17 | Herat | Center | 15 | 9 | 0 | 9 | 4 | . PAIL's livestock department | . Farmers, NHLP, private sector | Completed | Planning costs charged.
Herat | C3.3c(b)-054-HER | C8.3c(b)-054-HER | 3 | Exposure visit to Nangarhar - Honey | This activity swaped to trainings with cosent of EDU. Under this activity 7 different trainings in Grapes VC are conducted.Injil:2 trainings 31+32=63 Guzara:2 trainings 31+32=63 farmers Zenda jan: 1 training 31 farmers Karukh : 1 training 32 Pashtoon Zarghon: 1 training 31 farmers Total Demo Gardens 7trainnigs Total Beneficiaries: 220 Gardeners. Trainings subjects will be pre-harvest, Harvest and Post-harvest/Marketing as below table: | Visit |  | - | - | - | - | 3.3c.1 | 1 | 1 | Visits (No) | Apri,17 | Sept,17 | 28/2/18 | 2018-05-03 | Herat | Center | 15 | 220 | 0 | 220 | 4 | . PAIL's livestock department | . Farmers, NHLP, private sector | Completed
Herat | C3.3c(c)-055-HER | C8.3c(c)-055-HER | 3 | Exposur visit to Kandahar | Participants list is prepared | Visit |  | - | - | - | - | 3.3c.1 | 1 | 1 | Visits (No) | Apri,17 | Sept,17 | 2017-08-12 | 2017-08-15 | Herat | Center | 7 | 6 | 0 | 6 | 4 | . PAIL's livestock department | . Gardeners, Private sector and NHLP | Completed
Herat | C3.2a(c)-060-HER | C8.2a(c)-060-HER | 3 | VC Consultation workshop with different stakeholder - Input supplier workshop | Merged with activity 062 | Workshop |  |  | - | - |  | 3.2a.1 | 1 |  | Workshops (No.) | Apri,17 | Sept,17 | 20/12/17 | 20/12/17 | Herat | Center | 15 |  |  |  | 4 | . PAIL Department | . NHLP, Lead farmers and traders | Completed
Herat | C3.3f(a)-061-HER | C8.3f(a)-061-HER | 3 | Workshop for identification of input supplies challenges |  | Workshop |  |  | - | - | - | 3.1b.1 | 1 | 1 | Workshops (No.) | Apri,17 | Sept,17 | 30/7/17 | 30/7/17 | Herat | Center | 20 | 21 | 2 | 23 | 4 | . PAIL plan protection and Quarantine | . Lead farmers, Traders and AAIP | Completed
Herat | C3.3f(b)-062-HER | C8.3f(b)-062-HER | 3 | Workshop for identification of input supplies challenges | Third week of Dec (60 & 62) | Workshop |  |  | - | - | - | 3.3.f.3 | 1 |  | Workshops (No.) | Apri,17 | Sept,17 | 20/12/17 | 20/12/17 | Herat | Center | 20 | 45 | 1 | 46 | 4 | . PAIL plan protection and Quarantine | . Lead farmers, Traders and AAIP | Completed
Balkh | C3.3b(a)-033-MZR | C7.3b(a)-033-MZR | 3 | Technical training to farmers in selected VCs - Almond VC | next week | Training |  | - | - | - | - | 3.3b.1 | 1 | 1 | Trainings (No.) | Apri,17 | Sept,17 | 2017-11-07 | 2017-11-07 | Balkh | Balkh | 15 | 20 | 0 | 20 | 7 | • PAIL Directorate | NHLP , SNaPP2 and GIZ SEDEP/GFA | Completed
Balkh | C3.3b(b)-034-MZR | C7.3b(b)-034-MZR | 3 | Technical training to farmers in selected VCs - Almond VC |  | Training |  | - | - | - | - | 3.3b.1 | 1 | 1 | Trainings (No.) | Apri,17 | Sept,17 | 2017-08-11 | 2017-08-11 | Balkh | Balkh | 15 | 17 | 0 | 17 | 7 | • PAIL Directorate | NHLP , SNaPP2 and GIZ SEDEP/GFA | Completed
Balkh | C3.3b(c)-035-MZR | C7.3b(c)-035-MZR | 3 | Technical training to farmers in selected VCs - Almond VC |  | Training |  | - | - | - | - | 3.3b.1 | 1 | 1 | Trainings (No.) | Apri,17 | Sept,17 | 22/11/17 | 22/11/17 | Balkh | Dehdadi | 15 | 17 | 0 | 17 | 7 | • PAIL Directorate | NHLP , SNaPP2 and GIZ SEDEP/GFA | Completed
Balkh | C3.3b(d)-036-MZR | C7.3b(d)-036-MZR | 3 | Technical training to farmers in selected VCs - Almond VC | Training and an activity wherer farmers where taken to other almond orchards where pollination practices are implemented. | Training |  | - | - | - | - | 3.3b.1 | 1 |  | Trainings (No.) | Apri,17 | Sept,17 | 21/11/17 | 21/11/17 | Balkh | Dehdadi | 15 | 21 | 0 | 21 | 7 | • PAIL Directorate | NHLP , SNaPP2 and GIZ SEDEP/GFA | Completed
Balkh | C3.3b(e)-037-MZR | C7.3b(e)-037-MZR | 3 | Technical training to farmers in selected VCs - Almond VC |  | Training |  | - | - | - | - | 3.3b.1 | 1 | 1 | Trainings (No.) | Apri,17 | Sept,17 | 28/11/17 | 28/11/17 | Balkh | Dehdadi | 15 | 20 | 0 | 20 | 7 | • PAIL Directorate | NHLP , SNaPP2 and GIZ SEDEP/GFA | Completed
Balkh | C3.3b(f)-038-MZR | C7.3b(f)-038-MZR | 3 | Technical training to farmers in selected VCs - Almond VC |  | Training |  | - | - | - | - | 3.3b.1 | 1 | 1 | Trainings (No.) | Apri,17 | Sept,17 | 29/11/17 | 29/11/17 | Balkh | Nahre-e-Shahi | 15 | 16 | 0 | 0 | 7 | • PAIL Directorate | NHLP , SNaPP2 and GIZ SEDEP/GFA | Completed
Balkh | C3.3b(g)-039-MZR | C7.3b(g)-039-MZR | 3 | Technical training to farmers in selected VCs - Almond VC | Khulum District | Training |  | - | - | - | - | 3.3b.1 | 1 | 1 | Trainings (No.) | Apri,17 | Sept,17 | 2017-10-31 | 2017-10-31 | Balkh | Nahre-e-Shahi | 15 | 25 | 0 | 25 | 7 | • PAIL Directorate | NHLP , SNaPP2 and GIZ SEDEP/GFA | Completed
Balkh | C3.3b(h)-040-MZR | C73b(h)-040-MZR | 3 | Technical training to farmers in selected VCs - Almond VC |  | Training |  | - | - | - | - | 3.3b.1 | 1 | 1 | Trainings (No.) | Apri,17 | Sept,17 | 2017-01-11 | 2017-01-11 | Balkh | Balkh | 15 | 22 | 0 | 22 | 7 | • PAIL Directorate | NHLP , SNaPP2 and GIZ SEDEP/GFA | Completed
Balkh | C3.3b(i)-041-MZR | C7.3b(i)-041-MZR | 3 | Technical training to farmers in selected VCs - Tomato Paste |  | Training |  | - | - | - | - | 3.3b.1 | 1 | 1 | Trainings (No.) | Apri,17 | Sept,17 | 25/09/17 | 26/09/17 | Balkh | Balkh | 15 | 0 | 34 | 34 | 7 | • PAIL Directorate | NHLP , SNaPP2 and GIZ SEDEP/GFA | Completed
Balkh | C3.3b(j)-042-MZR | C7.3b(j)-042-MZR | 3 | Technical training to farmers in selected VCs - Jam |  | Training |  | - | - | - | - | 3.3b.1 | 1 | 1 | Trainings (No.) | Apri,17 | Sept,17 | 27/09/17 | 28/09/17 | Balkh | Balkh | 15 | 0 | 34 | 34 | 7 | • PAIL Directorate | NHLP , SNaPP2 and GIZ SEDEP/GFA | Completed
Balkh | C3.3b(k)-043-MZR | C7.3b(k)-043-MZR | 3 | Technical training to farmers in selected VCs - Saffron |  | Training |  | - | - | - | - | 3.3b.1 | 1 | 1 | Trainings (No.) | Apri,17 | Sept,17 | 2017-10-22 | 2017-10-22 | Balkh | Dehdadi | 15 | 33 | 1 | 34 | 7 | • PAIL Directorate | NHLP , SNaPP2 and GIZ SEDEP/GFA | Completed
Balkh | C3.3b(l)-044-MZR | C7.3b(l)-044-MZR | 3 | Technical training to farmers in selected VCs - Saffron |  | Training |  | - | - | - | - | 3.3b.1 | 1 | 1 | Trainings (No.) | Apri,17 | Sept,17 | 2017-10-21 | 2017-10-21 | Balkh | Dehdadi | 15 | 30 | 1 | 31 | 7 | • PAIL Directorate | NHLP , SNaPP2 and GIZ SEDEP/GFA | Completed
Balkh | C3.3b(m)-045-MZR | C7.3b(m)-045-MZR | 3 | Technical training to farmers in selected VCs - Saffron | next week | Training |  | - | - | - | - | 3.3b.1 | 1 | 1 | Trainings (No.) | Apri,17 | Sept,17 | 2017-10-23 | 2017-10-23 | Balkh | Khulum | 15 | 2 | 28 | 30 | 7 | • PAIL Directorate | NHLP , SNaPP2 and GIZ SEDEP/GFA | Completed
Balkh | C3.3b(n)-046-MZR | C7.3b(n)-046-MZR | 3 | Technical training to farmers in selected VCs - Food Processing - pickel | Food Processing Evaluation Workshop | Training |  | - | - | - | - | 3.3b.1 | 1 | 1 | Trainings (No.) | Apri,17 | Sept,17 | 19/12/17 | 19/12/17 | Balkh | Nahre-e-Shahi | 15 | 0 | 22 | 22 | 7 | • PAIL Directorate | NHLP , SNaPP2 and GIZ SEDEP/GFA | Completed
Balkh | C3.3b(0)-047-MZR | C7.3b(0)-047-MZR | 3 | Technical training to farmers in selected VCs | Almond- Oil treatment workshop | Training |  | - | - | - | - | 3.3b.1 | 1 | 1 | Trainings (No.) | Apri,17 | Sept,17 | 23/01/18 | 23/01/18 | Balkh | Nahre-e-Shahi | 15 | 24 | 0 | 24 | 7 | • PAIL Directorate | NHLP , SNaPP2 and GIZ SEDEP/GFA | Completed
Balkh | C3.3b(p)-048-MZR | C7.3b(p)-048-MZR | 3 | Technical training to farmers in selected VCs | Pollination consultation workshop | Training |  | - | - | - | - | 3.3b.1 | 1 |  | Trainings (No.) | Apri,17 | Sept,17 | 14/01/18 | 14/01/18 | Balkh | Balkh | 15 | 33 | 0 | 33 | 7 | • PAIL Directorate | NHLP , SNaPP2 and GIZ SEDEP/GFA | Completed
Balkh | C3.3b(q)-049-MZR | C7.3b(q)-049-MZR | 3 | Technical training to farmers in selected VCs | Almond- Oil treatment workshop | Training |  | - | - | - | - | 3.3b.1 | 1 | 1 | Trainings (No.) | Apri,17 | Sept,17 | 2018-04-02 | 2018-04-02 | Balkh | Balkh - Hewad village | 15 | 20 | 0 | 20 | 7 | • PAIL Directorate | NHLP , SNaPP2 and GIZ SEDEP/GFA | Completed
Balkh | C3.3b(r)-050-MZR | C7.3b(r)-050-MZR | 3 | Technical training to farmers in selected VCs | Almond- Oil treatment workshop | Training |  | - | - | - | - | 3.3b.1 | 1 | 1 | Trainings (No.) | Apri,17 | Sept,17 | 2018-05-02 | 2018-05-02 | Balkh | Balkh- Chahar Sang | 15 | 20 | 0 | 20 | 7 | • PAIL Directorate | NHLP , SNaPP2 and GIZ SEDEP/GFA | Completed
Balkh | C3.3b(s)-051-MZR | C7.3b(s)-051-MZR | 3 | Technical training to farmers in selected VCs | Almond- Oil treatment workshop | Training |  | - | - | - | - | 3.3b.1 | 1 | 1 | Trainings (No.) | Apri,17 | Sept,17 | 2018-06-02 | 2018-06-02 | Balkh | Balkh- Shaab Turkmania | 15 | 20 | 0 | 20 | 7 | • PAIL Directorate | NHLP , SNaPP2 and GIZ SEDEP/GFA | Completed
Balkh | C3.1c(a)-054-MZR | C7.1c(a)-054-MZR | 3 | Workshop on ISO Standards | Implementation in December | Workshop |  | - | - | - |  | 3.1c.2 | 1 |  | Workshops (No.) | Apri,17 | Sept,17 | 20/12/17 | 20/12/17 | Balkh | Balkh | 50 | 25 | 2 | 27 | 7 | • PAIL Directorate | NHLP , SNaPP2 and GIZ SEDEP/GFA | Completed | Planning costs charged.
Balkh | C3.3c(a)-055-MZR | C7.3c(a)-055-MZR | 3 | Exposur visit | to Herat in Saffron VC | Visit |  | - | - | - | - | 3.3c.1 | 1 |  | Visits (No) | Apri,17 | Sept,17 | 19/11/17 | 23/11/17 | Balkh | Center | 4 | 5 | 1 | 6 | 7 | • PAIL Directorate | NHLP | Completed
Balkh | C3.2a(a)-058-MZR | C7.2a(a)-058-MZR | 3 | VC Consultation workshop with different stakeholder - Saffron VC | A draft MOU has been signed with project partners on Saffron and Almond value chains | Workshop |  |  | - | - |  | 3.2a.1 | 1 | 1 | Workshops (No.) | Apri,17 | Sept,17 | 2017-08-07 | 2017-08-07 | Balkh | Center | 15 | 28 | 7 | 35 | 7 | • PAIL Directorate | NHLP, SNaPP2, GIZ SEDEP/GFA, UN-ILO, RADAP North, SDO, CARD-F , ADF, DOCI, BCCI, and DOWA | Completed
Balkh | C3.2a(b)-059-MZR | C7.2a(b)-059-MZR | 3 | VC Consultation workshop with different stakeholder - Almond VC |  | Workshop |  |  | - | - |  | 3.2a.1 | 1 | 1 | Workshops (No.) | Apri,17 | Sept,17 | 2017-08-13 | 2017-08-13 | Balkh | Center | 15 | 35 | 1 | 36 | 7 | • PAIL Directorate | NHLP, SNaPP2, GIZ SEDEP/GFA, UN-ILO, RADAP North, SDO, CARD-F , ADF, DOCI, BCCI, and DOWA | Completed
Balkh | C3.2a(c)-060-MZR | C7.2a(c)-060-MZR | 3 | VC Consultation workshop with different stakeholder - Food processing women |  | Workshop |  |  | - | - |  | 3.2a.1 | 1 | 1 | Workshops (No.) | Apri,17 | Sept,17 | 2017-08-16 | 2017-08-16 | Balkh | Center | 15 | 4 | 26 | 30 | 7 | • PAIL Directorate | NHLP, SNaPP2, GIZ SEDEP/GFA, UN-ILO, RADAP North, SDO, CARD-F , ADF, DOCI, BCCI, and DOWA | Completed
Balkh | C3.3f(a)-061-MZR | C7.3f(a)-061-MZR | 3 | Workshop for identification of input supplies challenges |  | Workshop |  |  | - | - |  | 3.3.f.3 | 1 | 1 | Workshops (No.) | Apri,17 | Sept,17 | 2017-08-30 | 2017-08-30 | Balkh | Center | 20 | 39 | 2 | 41 | 7 | • PAIL Directorate | NHLP, SNaPP2 and AAIP | Completed
Kandahar | C1.1b(a)-014-KND |  | 1 | Establichment of PC |  | PC Meeting |  |  | - | - |  | 1.1b.2 | 1 | 1 | Committee (No.) | Apri,17 | Sept,17 | 2017-05-02 | 2017-05-02 | Kandahar | Center | 30 | 19 | 1 | 20 | MC | • PAIL Directorate | • PRRD • Citizen Charter deportment (PRRD) • Women Affair Directorate •ACCI representatives •Agriculture faculty • Other relevant projects such us (NHLP , AAIP, OFWM, Mercy Corps, SNaPP2, AAIP, CARD-F, ILO, AAEP, GFA, LML, ...) | Completed
Kandahar | C1.1b(b)-015-KND |  | 1 | Conduct PC Meeting (Kandahar) |  | PC Meeting |  |  | - | - |  | 1.1b.3 | 1 | 1 | Meetings (No.) | Apri,17 | Sept,17 | 2017-08-23 | 2017-08-23 | Kandahar | Center | 45 | 30 | 1 | 31 | MC | • PAIL Directorate | • PRRD • Citizen Charter deportment (PRRD) • Women Affair Directorate •ACCI representatives •Agriculture faculty • Other relevant projects such us (NHLP , AAIP, OFWM, Mercy Corps, SNaPP2, AAIP, CARD-F, ILO, AAEP, GFA, LML, ...) | Completed
Kandahar | C3.1a(b)-017-KND |  | 3 | develop VC reports (Pomegrante and Grap) |  | Workshop |  |  | - | - |  | 3.1a.2 | 1 | 1 | Value chain (No.) | Apri,17 | Sept,17 | 2017-06-14 | 2017-06-14 | Kandahar | Center | 40 | 27 | 1 | 28 | MC | • General Directorate for Planning and Program Coordination, Co-chair (MAIL) • General Directorate of Extension, Member (MAIL) • Directorate of private sector development ( MAIL) • ARIA (MAIL) AJ6:AK61 | • Bilateral fund management deportment/Citizen Charter, Member (MRRD) • MoCI • Directorate of Alternative Livelihood (MoCN) • Afghan Chamber of Commerce and Industries (ACCI) • General Directorate of Budget, Member (MoFA) • European Union Delegation, Member (EU Kabul Office) • NHLP, Member | Completed
Kandahar | C3.1b(a)-018-KND |  | 3 | Develop Partcipatory Market System Development |  | Workshop |  |  | - | - |  | 3.1b.1 | 1 | 1 | Workshops (No.) | Apri,17 | Sept,17 | 2017-05-16 | 2017-05-16 | Kandahar | Daman | 35 | 23 | 0 | 23 | MC | • PAIL Directorate | • PRRD • Citizen Charter deportment (PRRD) • Women Affair Directorate •ACCI representatives •Agriculture faculty • Other relevant projects such us (NHLP , AAIP, OFWM, Mercy Corps, SNaPP2, AAIP, CARD-F, ILO, AAEP, GFA, LML, ...) | Completed
Kandahar | C3.1b(b)-019-KND |  | 3 | Develop Partcipatory Market System Development |  | Workshop |  |  | - | - |  | 3.1b.1 | 1 | 1 | Workshops (No.) | Apri,17 | Sept,17 | 2017-07-04 | 2017-07-04 | Kandahar | Daman | 35 | 35 | 0 | 35 | MC | • PAIL Directorate | • PRRD • Citizen Charter deportment (PRRD) • Women Affair Directorate •ACCI representatives •Agriculture faculty • Other relevant projects such us (NHLP , AAIP, OFWM, Mercy Corps, SNaPP2, AAIP, CARD-F, ILO, AAEP, GFA, LML, ...) | Completed
Kandahar | C3.1b(c)-020-KND |  | 3 | Conduct workshop for identifying gaps in agr.inputs |  | Workshop |  |  | - | - |  | 3.1b.3 | 1 | 1 | Agriculture plan (No.) | Apri,17 | Sept,17 | 2017-07-18 | 2017-07-18 | Kandahar | Center | 40 | 42 | 0 | 42 | MC | • PAIL Directorate | • PRRD • Citizen Charter deportment (PRRD) • Women Affair Directorate •ACCI representatives •Agriculture faculty • Other relevant projects such us (NHLP , AAIP, OFWM, Mercy Corps, SNaPP2, AAIP, CARD-F, ILO, AAEP, GFA, LML, ...) | Completed
Kandahar | C3.2b(a)-021-KND |  | 3 | Identifying 2 private entrepreneurs |  | Workshop |  |  | - | - |  | 3.1b.1 | 1 |  | Workshops (No.) | Apri,17 | Sept,17 | 2017-10-05 | 2017-10-05 | Kandahar | Center | 35 | 33 | 0 | 33 | MC |  |  | Completed
Kandahar | C3.3a(a)-022-KND |  | 3 | Idenify business agriculture opportuntiies |  | Workshop |  |  | - | - |  | 3.1b.1 | 1 | 1 | Workshops (No.) | Apri,17 | Sept,17 | 2017-07-31 | 2017-07-31 | Kandahar | Center | 20 | 20 | 0 | 20 | MC | • General Directorate for Planning and Program Coordination (MAIL) • General Directorate of Extension, Member (MAIL) • Directorate of Communication (MAIL) | • MRRD • Citizen Charter Program (MRRD) • Directorate of Communication (MAIL) •NHLP • Other involved projects in implementation of cross ministerial projects. | Completed
Kandahar | C3.3b(a)-023-KND |  | 3 | Technical training to farmers in selected VCs |  | Training |  |  | - | - |  | 3.3b.1 | 1 |  | Trainings (No.) | Apri,17 | Sept,17 | 2017-12-09 | 13/09/17 | Kandahar | Center | 40 | 46 | 0 | 46 | MC | MAIL, DAIL | NHLP, Traders, Associations, RADP-S | Completed
Kandahar | C3.3b(b)-024-KND |  | 3 | Technical training to farmers in selected VCs |  | Training |  |  | - | - |  | 3.3b.1 | 1 | 1 | Trainings (No.) | Apri,17 | Sept,17 | 2017-08-08 | 2017-08-08 | Kandahar | Center | 40 | 40 | 0 | 40 | MC | MAIL, DAIL | NHLP, Traders, Associations, RADP-S | Completed
Kandahar | C3.3b(c)-025-KND |  | 3 | Event for identifying the current constraints for linkages in VCs |  | Workshop |  |  | - | - |  | 3.3c.1 | 1 | 1 | Visits (No) | Apri,17 | Sept,17 | 20/09/17 | 20/09/17 | Kandahar | Center | 45 | 40 | 0 | 40 | MC | MAIL, DAIL | NHLP, Traders, Associations, RADP-S | Completed
Kandahar | C3.1b(d)-026-KND |  | 3 | Develop Partcipatory Market System Development |  | Workshop |  |  | - | - |  | 3.1b.1 | 1 | 1 | Workshops (No.) | Apri,17 | Sept,17 | 2017-05-23 | 2017-05-23 | Kandahar | Spin Boldak | 30 | 30 | 0 | 30 | MC | • PAIL Directorate | • PRRD • Citizen Charter deportment (PRRD) • Women Affair Directorate •ACCI representatives •Agriculture faculty • Other relevant projects such us (NHLP , AAIP, OFWM, Mercy Corps, SNaPP2, AAIP, CARD-F, ILO, AAEP, GFA, LML, ...) | Completed
Kandahar | C3.3c(a)-027-KND |  | 3 | B2B Meeting and linkage |  | Workshop |  |  | - | - |  | 3.3c.1 | 1 | 1 | Workshops (No.) | Apri,17 | Sept,17 | 2017-08-17 | 2017-08-17 | Kandahar | Center | 45 | 39 | 0 | 39 | MC | MAIL, DAIL | NHLP, Traders, Associations, RADP-S | Completed
Helmand | C1.1b(a)-009-HEL |  | 1 | Establichment of PC |  | PC Meeting |  |  | - | - |  | 1.1b.2 | 1 | 1 | Committee (No.) | Apri,17 | Sept,17 | 2017-05-14 | 2017-05-14 | Helmand | Center | 35 | 20 | 0 | 20 | MC | • PAIL Directorate | • PRRD • Citizen Charter deportment (PRRD) • Women Affair Directorate •ACCI representatives •Agriculture faculty • Other relevant projects such us (NHLP , AAIP, OFWM, Mercy Corps, SNaPP2, AAIP, CARD-F, ILO, AAEP, GFA, LML, ...) | Completed
Helmand | C1.1b(b)-010-HEL |  | 1 | Conduct PC Meeting |  | PC Meeting |  |  | - | - |  | 1.1b.3 | 1 | 1 | Meetings (No.) | Apri,17 | Sept,17 | 2017-08-24 | 2017-08-24 | Helmand | Center | 45 | 31 | 1 | 32 | MC | • PAIL Directorate | • PRRD • Citizen Charter deportment (PRRD) • Women Affair Directorate •ACCI representatives •Agriculture faculty • Other relevant projects such us (NHLP , AAIP, OFWM, Mercy Corps, SNaPP2, AAIP, CARD-F, ILO, AAEP, GFA, LML, ...) | Completed
Helmand | C3.1a(a)-011-HEL |  | 3 | Develop VC report for grapes and pomogrante |  | Workshop |  |  | - | - |  | 3.1a.1 | 1 |  | District profiles (No.) | Apri,17 | Sept,17 | 2017-06-21 | 2017-06-21 | Helmand | Center | 40 | 40 | 0 | 40 | MC | • General Directorate for Planning and Program Coordination, Co-chair (MAIL) • General Directorate of Extension, Member (MAIL) • Directorate of private sector development ( MAIL) • ARIA (MAIL) AJ6:AK61 | • Bilateral fund management deportment/Citizen Charter, Member (MRRD) • MoCI • Directorate of Alternative Livelihood (MoCN) • Afghan Chamber of Commerce and Industries (ACCI) • General Directorate of Budget, Member (MoFA) • European Union Delegation, Member (EU Kabul Office) • NHLP, Member | Completed | Pomegranates & Grapes Value Chain Assessment Workshop, Helmand
Helmand | C3.1b(a)-012-HEL |  | 3 | Develop Partcipatory Market System Development |  | Workshop |  |  | - | - |  | 3.1b.1 | 1 | 1 | Workshops (No.) | Apri,17 | Sept,17 | 2017-05-24 | 2017-05-24 | Helmand | Nawa | 35 | 30 | 0 | 30 | MC | • PAIL Directorate | • PRRD • Citizen Charter deportment (PRRD) • Women Affair Directorate •ACCI representatives •Agriculture faculty • Other relevant projects such us (NHLP , AAIP, OFWM, Mercy Corps, SNaPP2, AAIP, CARD-F, ILO, AAEP, GFA, LML, ...) | Completed
Helmand | C3.1b(b)-013-HEL |  | 3 | Sign MoU with Input suppliers |  | Workshop |  |  | - | - |  | 3.1b.1 | 1 | 1 | Workshops (No.) | Apri,17 | Sept,17 | 2017-11-10 | 2017-11-10 | Helmand | Center | 45 | 30 | 30 |  | MC | • PAIL Directorate | • PRRD • Citizen Charter deportment (PRRD) • Women Affair Directorate •ACCI representatives •Agriculture faculty • Other relevant projects such us (NHLP , AAIP, OFWM, Mercy Corps, SNaPP2, AAIP, CARD-F, ILO, AAEP, GFA, LML, ...) | Completed
Helmand | C3.2b(a)-014-HEL |  | 3 | Identifying 2 private entrepreneurs |  | Workshop |  |  | - | - |  | 3.1b.1 | 1 | 1 | Workshops (No.) | Apri,17 | Sept,17 | 13/09/17 | 14/09/17 | Helmand | Center | 35 | 45 | 0 | 45 | MC |  |  | Completed
Helmand | C3.3a(a)-015-HEL |  | 3 | Idenify business agriculture opportuntiies are identified and characterized for adoption by entreprenurs. |  | Workshop |  |  | - | - |  | 3.1b.1 | 1 |  | Workshops (No.) | Apri,17 | Sept,17 | 2017-07-13 | 2017-07-13 | Helmand | Center | 20 | 20 | 0 | 20 | MC | • General Directorate for Planning and Program Coordination (MAIL) • General Directorate of Extension, Member (MAIL) • Directorate of Communication (MAIL) | • MRRD • Citizen Charter Program (MRRD) • Directorate of Communication (MAIL) •NHLP • Other involved projects in implementation of cross ministerial projects. | Completed
Helmand | C3.3b(a)-016-HEL |  | 3 | Technical training to inputsuppliers, DAIL staff |  | Training |  |  | - | - |  | 3.3b.1 | 1 | 1 | Trainings (No.) | Apri,17 | Sept,17 | 2017-07-12 | 2017-07-12 | Helmand | Center | 40 | 42 | 0 | 42 | MC | MAIL, DAIL | NHLP, Traders, Associations, RADP-S | Completed
Helmand | C3.3b(b)-017-HEL |  | 3 | Technical training to inputsuppliers, DAIL staff |  | Training |  |  | - | - |  | 3.3b.1 | 1 | 1 | Trainings (No.) | Apri,17 | Sept,17 | 2017-08-10 | 2017-08-10 | Helmand | Center | 40 | 40 | 0 | 40 | MC | MAIL, DAIL | NHLP, Traders, Associations, RADP-S | Completed
Helmand | C3.3c(a)-018-HEL |  | 3 | B2B Meeting and linkage |  | Linkage Meeting |  |  | - | - |  | 3.3c.1 | 1 | 1 | Meetings (No.) | Apri,17 | Sept,17 | 2017-08-17 | 2017-08-17 | Helmand | Center | 45 | 40 | 0 | 40 | MC | MAIL, DAIL | NHLP, Traders, Associations, RADP-S | Completed
Helmand | C3.3c(b)-019-HEL |  | 3 | B2B Meeting and linkage |  | Linkage Meeting |  |  | - | - |  | 3.3c.1 | 1 |  | Meetings (No.) | Apri,17 | Sept,17 | 26/09/17 | 26/09/17 | Helmand | Center | 45 | 45 | 0 | 45 | MC | MAIL, DAIL | NHLP, Traders, Associations, RADP-S | Completed
Kabul | N/A | C1.5b(j)-071-KBL | 1 | Translation |  | Services | [22 empty] | Completed
Kabul | N/A | C5.4a(a)-072-KBL | 3 | Data Collection |  | Services | [22 empty] | Completed
Nangarhar |  | C6.3c(b)-054-JAA | 3 | Expousre visit to India - Onion VC |  | Training | [5 empty] | 3.3c4 | 1 | 1 | expsoure vist (No.) | 15/4/18 | 22/4/18 |  |  | Nangarhar | [8 empty] | Completed
Nangarhar |  | C6.3c(c)-055-JAA | 3 | Exposure Visit to Inida - Onion VC |  | Training | [5 empty] | 3.3c4 | 1 |  | expsoure vist (No.) |  |  |  |  | Nangarhar
Kabul | N/A | C1.5b(i)-070-KBL | 1 | Knowledge Bank |  | services | [5 empty] | 1.5b.2 | 1 | [6 empty] | Kabul | Center | [7 empty] | completed
|  | C5.3c(d)-070-KBL | 3
Kabul | C3.3c(b)-069-KBL | C5.3c(b)-069-KBL | 3 | Expsoure Visit to Tajikistan MAIL High ranking officials - cold storages |  | visit |  | - | - | - | - | 3.3c.1 | 1 |  | Visits (No) | Apri,17 | Sept,17 |  |  | Kabul | Center | 7 | 7 | 0 | 7 | 6 | MAIL, DAIL | MAIL, MoE, MRRD | completed

## Codes
Component | EUD Approval | Responsible Person | Status | Color | Provinces | Type of Activity | Indicator Number | Components | Measurement Unit
One | Yes | 1 | On-going |  | Badakhshan | Training | 1 | 1899-12-31 | Percentage (%)
Three | No | 2 | Pending |  | Badghis | Visit | 2 | 1900-01-02 | Farmers (No.)
|  | 3 | Completed |  | Baghlan | Workshop | 1.1 |  | Procedures (No.)
|  | 4 | Dropped |  | Balkh | PSC Meeting | 1.2 |  | Model (No.)
|  | 5 |  |  | Bamyan | PC Meeting | 2.1 |  | Agreement (No.)
|  | 6 |  |  | Daykundi | Exposure visit | R1.1 |  | Strategy (No.)
|  | 7 |  |  | Farah | Linkage Meeting | R1.2 |  | Input suppliers (No.)
|  | 8 |  |  | Faryab | Procurement of goods | R.1.3 |  | Committee (No.)
|  | 9 |  |  | Ghazni | Analysis | R1.4 |  | Meetings (No.)
|  | 10 |  |  | Ghor | Policy development | R.3.2 |  | Workshops (No.)
|  | 11 |  |  | Helmand | Materials development | R3.3 |  | Trainings (No.)
|  | 12 |  |  | Herat | Services | R3.4 |  | MAIL staff (No.)
|  | 13 |  |  | Jowzjan | Others | 1.1a.1 |  | Curriculum(No.)
|  | 14 |  |  | Kabul |  | 1.1a.2 |  | PPP (No.)
|  | 15 |  |  | Kandahar |  | 1.1a.3 |  | Persons (No.)
|  | 16 |  |  | Kapisa |  | 1.1b.1 |  | Concept Note (No.)
|  | MC |  |  | Khost |  | 1.1b.2 |  | Research Tours (No.)
|  | 9 & 11 |  |  | Kunar |  | 1.1b.3 |  | Assessment (No.)
|  | 3 & 11 |  |  | Kunduz |  | 1.1b.3.1 |  | Digital Library (No.)
[5 empty] | Laghman |  | 1.1b.3.2 |  | District profiles (No.)
[5 empty] | Logar |  | 1.1.c.1 |  | Value chain (No.)
[5 empty] | Maidan Wardak |  | 1.1d.1 |  | Strategies (No.)
[5 empty] | Nangarhar |  | 1.2a.1 |  | Agriculture plan (No.)
[5 empty] | Nimruz |  | 1.2a.2 |  | Packages (No.)
[5 empty] | Nuristan |  | 1.2b.1 |  | Reforms (No.)
[5 empty] | Paktia |  | 1.2.b.2 |  | Roundtable meetings (No.)
[5 empty] | Paktika |  | 1.2b.3 |  | Visits (No)
[5 empty] | Panjshir |  | 1.2c.1 |  | Study trips (No.)
| Total SNKE days | 400 |  |  | Parwan |  | 1.2c.2 |  | Business Plan
| Total JNKE days | 800 |  |  | Samangan |  | 1.2d.1 |  | Business opportunities (No.)
[5 empty] | Sar-e Pol |  | 1.2d.2 |  | B2B events (No.)
[5 empty] | Takhar |  | 1.2e.1 |  | Regulation doc (No.)
[5 empty] | Urozgan |  | 1.2e.2 |  | Products (No.)
[5 empty] | Zabul |  | 1.3a.1 |  | Success stories
1.3a.1.1
1.3a.2
1.3b.1
1.4a.1
1.4b.2
1.4b2.1
1.4c.3
1.4c.3.1
1.4d.4
1.4d.5
1.4e.6
1.5a.1
1.5a.1.1
1.5b.1
1.5b.2
1.5c.1
3.1a.1
3.1a.2
3.1b.1
3.1b.2
3.1b.3
3.1c.1
3.1c.2
3.1c.3
3.1c.4
3.2a.1
3.2b.1
3.2b.1
3.2b.2
3.3a.1
3.3a.2
3.3b.1
3.3c.1
3.3c.2
3.3d.1
3.3e.1
3.3f.1
3.3f.2
3.3.f.3
3.3g.1
3.3g.2
3.4a.1
3.4b.1
3.4c.1