## Consolidated database
Completed
Province | Activity Code | Component | Activity | Comments | Type of Activity | Implementation Date (DD,MMM,YY) |  | District | Planned Participants | Actual Participants |  |  | Status | Remarks
[6 empty] | Start | End |  |  | Male | Female | Total
Kabul | C1.1a(c)-073-KBL | 1 | Organize PSC meeting |  | PSC Meeting | 16/12/18 | 16/12/18 | Center | 35 | 30 | 5 | 35 | completed
Kabul | C1.1b(i)-074-KBL | 1 | Organize PC meeting central region 4th Quarter 2017 | Held on 2nd October 2018 | PC meeting |  |  | Center | 35 |  |  |  | completed
Nangarhar | C2.1b(g)-056-JAA | 1 | Organize PC meeting Eastern region 4th Quarter 2017 |  | PC meeting | 13/5/18 | 13/5/18 | Center | 30 | 25 | 0 | 0 | completed
Nangarhar | C2.1b(h)-057-JAA | 1 | Organize PC meeting Eastern region 1st Quarter 2018 |  | PC meeting | 2018-03-10 | 2018-03-10 | Center | 30 | 18 | 0 | 18 | completed
Helmand | C2.1b(c)-020-HEL | 1 | Organize PC meeting Southern region 4th Quarter 2017 |  | PC meeting | 25/07/18 | 25/07/18 | Center | 30 | 38 | 0 | 38 | completed
Helmand | C2.1b(d)-021-HEL | 1 | Organize PC meeting Southern region 1st Quarter 2018 |  | PC meeting |  | 2019-03-11 | Center | 30 | 1 | 42 | 43 | completed
Balkh | C3.1b(g)-064-MZR | 1 | Organize PC meeting Northern region 4th Quarter 2017 | Beside PC meeting an FLRC workshop for 35 participants from different stakeholders including PAIL staff, MAIL related projects staff, CCNPP, private sectors, CDC heads, private Sector actors and EU-FARM staff participated | PC meeting | 2018-03-10 | 2018-03-10 | Center | 30 | 26 | 2 | 28 | completed
Balkh | C3.1b(h)-065-MZR | 1 | Organize PC meeting Northern region 1st Quarter 2018 |  | PC meeting | 27/06/19 | 27/06/19 | Center | 30 | 33 | 4 | 33 | completed
Herat | C4.1b(g)-063-HRT | 1 | Organize PC meeting Western region 4th Quarter 2017 | SNK1 visit to FLRC > SNKE1 Consultant visit - FLRC 5th Nov - 16th Nov 2018 | PC meeting | 2018-05-11 | 16/11/18 | Center | 30 |  |  |  | completed
Kabul | C1.2b(a)-078-KBL | 1 | Extension model and Extension Policy awareness workshop at central region (workshop on later stage of FLRC) | Used for some expenses of Travels and a workshop, it can be used for further Misc activities of such kind. - The activitiy is used for most of the FLRC workshops and relevant travel costs | Workshop | 19/02/19 | 19/02/19 | Center | 100 |  |  |  | completed
Nangarhar | C2.2b(a)-059-JAA | 1 | Extension model and Extension Policy awareness workshop at Eastren region (workshop on later stage of FLRC) | Keep it, it should also cover FLRC related visit to Herat, and lessen the budget, 8000 EUR would be enough. FLRC introductory workshop - HRT (17. 07.19) - Training location Hotel as it was guided by RMO to go for white listed locations. Location: Nangarhar Activity Code: C2. b2 (a)-059-JAA On 13th November 2019 an introductory workshop was conducted among the different CDCs members and other potential FLRC stakeholders in Nangarhar province. The aim of this workshop was to introduce EU-FARM FLRC model to members of CCDC/Agro Sub-committee and private sector, extension officers and partner projects in Kuz-Kunar district. During the workshop some of the CCDC members were asked regarding their role in the CCDC, unfortunately, most of them were not aware of their role. It was submitted by BRAC distirct manager “FARM team started their FLRC implementation ahead of BRAC plan for establishing CCDC. There are still some CCDC who didn’t collect their operation plan from the BRAC office. We are going to submit these plan to them in near future”. One of the member from Khalid Bin Waleed CCDC said that “I received a call from the CCDC head last night and he appointed me as head of agriculture committee within CCDC and we don’t know about our role and responsibilities yet”. Kuz Kunar agriculture staff along with the projects (SNaPP2, ONFWM, and NHLP) representatives submitted that the main problem here is that most of the times the responsible person of CCDC is not showing in all scheduled meetings and activities. Most of the times the responsible person is replaced by his siblings which has to be eliminated in the FLRC working group. Main findings of workshop: - FARM team find out the CCDC members were still not clear enough on FLRC model in the role therefore it’s decide that team will revisit all the CCDC/agro sub committees to identify and introduce the real volunteer and honest peoples to become the FLRC member in upcoming. Last time we visited only 10 CCDC’s with recommendation CCAPP IP-BRAC but look like we have dissimilar of interpretation of strong and weak CCDC, so therefore team decided to visit entire 20 CCDC’s that we find out the real strong CCDC for FLRC membership according to FARM criteria. - Agro Plan of each CCDC’s will review with each committees along with BRAC. - Confusion between action plan and job description each committee will clear in individual meetings with CCDS. Conclusion It is a good opportunity and a good start for FARM to start with FLRC activities as there is huge potential and interest for establishing FLRC. Location: Herat Activity Code: C4.2b (a)-066-HER On 3rd November 2019 FLRC meeting was held in Karakhu DAIL office among FLRC members. The aim of the meeting was to exchange information and improve coordination among the different stakeholder on district level. During this meeting representatives from NHLP, PRB, SNaPP2, DACAAR, SARD (FAO)/DAIL, Women’s Livestock Association, Honey and Horticulture Association, Private Seed Company, Livestock Association, CCNPP, Saffron Producer Association, Forestry Association, and EU FARM presented what has been accomplished and are their planned activities. In addition to this, DAIL Livestock Officer and DAIL Plant Protection Officer also briefed the participants regarding the main interventions that are planned for Karaukh district. During the meeting it was suggested that: - There has to be official identity for the FLRC which will help in keeping involved stakeholders accountable for what has been agreed among FLRC stakeholders. - More exchange visits has to be arranged among with different districts where farmers can learn best agriculture practices form the farmers they are expert in. Farmers that has been involved in almond production are keen to have a visit to Balkh and see the pre and post-harvest methods involved in almond value chain. - IN SUMMARY the FLRC working group thanked all meeting participants for their active participation and made below points: • There are a few NGOs working in the district that have not attended the meeting and they must do so for the next meeting with NGOs. • There is little coordination between NGOs and no linkages between them and associations in Herat. | Workshop | 10.07.2019 | 10.07.2019 | Center | 100 |  |  |  | completed
Herat | C4.2b(a)-066-HER | 1 | Extension model and Extension Policy awareness workshop at western region (workshop on later stage of FLRC) | Used for FLRC miscellaneous activities / SNKE1 conducted FLRC orientation workshops (one in each location) - EU FARM Sector Governance and Knowledge Management Consultant paid a visit to Herat Province and met with senior leadership of PAIL and other relevant stakeholders who are actively involved in matters of FLRCs. The visit started on 5th Nov and lasted until 16th Nov 2018 - FLRC meeting Zenda Jan December, 2019 - FLRC Partnership and Coordination Conference MAIL & MRRD December, 2019 On 16 September 10th FLRC meeting was conducted among Zinda A two-days practical training (30th & 31th August) was organized to 8 female food processors from On the 3rd August, a district agriculture planning workshop was organized in Zinda Jan district of Herat - FLRC orientation workshops in Hereat PIAL, Zinda Jan DAIL, and Karokh DAIL with the relevant stakeholder of FLRC on 9th, 10th and 11th December 2018. -EU FARM team held a meeting with FLRC members in Karokh District on 24th Feb 2019. EU FARM team held a meeting with FLRC members in Zinda Jan District on 20th Feb 2019 -- A meeting of the members of the FLRC working group including district Manager of CHA, SNaPP 2 Extension Workers, Karoukh traders, Dr. Frank O’Sullivan, Omid Dowlaty and Ahmad Shoaib Shams from EU-FARM was held on 10th March 2019 The code was also used for 6 IPM training sessions in tomato VC using FLRC platform | Workshop | 2018-09-12 | 2018-11-12 | Herat PAIL, Zenda Jan DAIL & Karokh DAIL | 100 |  |  |  | completed
Balkh | C7.3b(t)-069-MZR | 3 | Training/Demonstrations Involving Technical Issue on Selected Value Chain in Northern Region. | Almond post-harvest training. | Training | 17.July.2018 |  | Balkh | 20 | 30 | 0 | 30 | completed
Balkh | C7.3b(u)-070-MZR | 3 | Training/Demonstrations Involving Technical Issue on Selected Value Chain in Northern Region. | Almond post-harvest training. | Training | 18.July.2018 |  | Khulum | 20 | 21 | 0 | 21 | completed
Balkh | C7.3b(v)-071-MZR | 3 | Training/Demonstrations Involving Technical Issue on Selected Value Chain in Northern Region. | Almond post-harvest training. | Training | 24.July.2018 |  |  | 20 | 19 | 0 | 19 | completed
Balkh | C7.3b(w)-072-MZR | 3 | Training/Demonstrations Involving Technical Issue on Selected Value Chain in Northern Region. | Almond post-harvest training. | Training | 26.July.2018 |  |  | 20 | 21 | 0 | 21 | completed
Balkh | C7.3b(x)-073-MZR | 3 | Training/Demonstrations Involving Technical Issue on Selected Value Chain in Northern Region. | Almond post-harvest training. | Training |  |  |  | 20 |  |  |  | completed
Balkh | C7.3b(y)-074-MZR | 3 | Training/Demonstrations Involving Technical Issue on Selected Value Chain in Northern Region. | Almond Pollination training | Training | 2019-04-03 | 2019-04-03 | Balkh - Hewad | 20 | 17 | 0 | 17 | completed
Balkh | C7.3b(z)-075-MZR | 3 | Training/Demonstrations Involving Technical Issue on Selected Value Chain in Northern Region. | Almond Pollination training | Training | 2019-05-03 | 2019-05-03 | Balkh-Charsang | 20 | 21 | 0 | 21 | completed
Balkh | CF.3b(a)-076-MZR | 3 | Training/Demonstrations Involving Technical Issue on Selected Value Chain in Northern Region. | Almond Pollination training Used for Almond Technical training Disease and Aphids Control in Khulum district (Sayad village) (Training’s Date:21 -April-2019 – Balkh district) Total Trained Participants 21 Participataion in the planning workshop NHLP almong VC. Niazi cost charged July, 19 | Training | 2019-06-03 | 2019-06-03 | Dehdadi | 20 | 18 | 0 | 18 | completed
Balkh | CF.3b(b)-077-MZR | 3 | Training/Demonstrations Involving Technical Issue on Selected Value Chain in Northern Region. | Almond Pollination training Used for Almond Technical training Disease and Aphids Control in 41 farmers from the two different districts (Markaz Dehdadi, Sher Abad, Hazar Jerib, Puli Babu, Chehil Gazi and Langar khana villages) were attended. Trainings date: 22 April, 2019 | Training | 2019-06-03 | 2019-06-03 | Nahre-e-Shahi | 20 | 20 | 0 | 20 | completed
Balkh | CF.3b(c)-078-MZR | 3 | Training/Demonstrations Involving Technical Issue on Selected Value Chain in Northern Region. | Almond Pollination training | Training | 2019-07-03 | 2019-07-03 | Khulam | 20 | 17 | 0 | 17 | completed
Balkh | CF.3b(d)-079-MZR | 3 | Training/Demonstrations Involving Technical Issue on Selected Value Chain in Northern Region. | Almond Pollination training Used for Almond Technical training Disease and Aphids Control in Balkh district (Hewad, Qalacha, Charsang villages,) (Training’s Date:18 -April-2019 – Balkh district) Total Trained Participants 78 ( Charsang 27, Hewad 25, Qalacha26) | Training | 18/4/19 | 18/4/19 | Balkh | 20 | 78 | 0 | 78 | completed
Balkh | CF.3b(e)-080-MZR | 3 | Training/Demonstrations Involving Technical Issue on Selected Value Chain in Northern Region. | IPM | Training | 18/12/18 | 18/12/18 | Khulum | 20 | 16 | 0 | 16 | completed
Balkh | CF.3b(f)-081-MZR | 3 | Training/Demonstrations Involving Technical Issue on Selected Value Chain in Northern Region. | IPM 27.08.19 cost of ANHDO team also charged to this activity. 3*30K=90K not added to the total | Training | 25/12/18 | 25/12/18 | Nahr-e-Saraj | 20 | 19 | 0 | 19 | completed
Balkh | CF.3b(g)-082-MZR | 3 | Training/Demonstrations Involving Technical Issue on Selected Value Chain in Northern Region. | IPM | Training | 19/12/19 | 19/12/19 | Dehdadi | 20 | 18 | 0 | 18 | completed
Balkh | CF.3b(h)-083-MZR | 3 | Training/Demonstrations Involving Technical Issue on Selected Value Chain in Northern Region. | IPM Almost post harvest training 07 August, 2019 almond value chain | Training | 17/12/18 | 17/12/18 | Balkh-Charsang | 20 | 15 | 0 | 15 | completed
Balkh | CF.3b(i)-084-MZR | 3 | Training/Demonstrations Involving Technical Issue on Selected Value Chain in Northern Region. | IPM Almost post harvest training 08 August, 2019 almond value chain | Training | 16/12/18 | 16/12/18 | Balkh- Hewad | 20 | 22 | 0 | 22 | completed
Balkh | CF.3b(j)-085-MZR | 3 | Training/Demonstrations Involving Technical Issue on Selected Value Chain in Northern Region. | IPM// Saffron Processing Center Roundtable Workshop 10/02/19 | Training | 26/12/18 | 26/12/18 | Balkh- Shahab | 20 | 18 | 0 | 18 | completed
Balkh | CF.3b(l)-087-MZR | 3 | Training/Demonstrations Involving Technical Issue on Selected Value Chain in Northern Region. | Almond pollination workshop/training - Use the code to cover of Samangan activity: meeting ANGO July, 2019 - use budget for conducting Food processing training. expect dated of training 21. August. 2019 | Training | 16/02/19 | 16/02/19 | Khulum, Balkh, Dehdadi, Mazar-e-Sharif, | 20 | 29 | 0 | 29 | completed
Balkh | CF.3b(n)-089-MZR | 3 | Training/Demonstrations Involving Technical Issue on Selected Value Chain in Northern Region. | Women food processing - Bookkeeping training | Training | 14/02/19 | 14/02/19 | Nahr-e-Shahi, Dehdadi, Mazar-e-Sharif | 20 | 0 | 23 | 23 | completed
Balkh | CF.3b(o)-090-MZR | 3 | Training/Demonstrations Involving Technical Issue on Selected Value Chain in Northern Region. | Training in Saffron VC - Male | Training | 2018-07-08 | 2018-07-08 | Balkh, Khulum, Nahre-e-Shahi, Dehdadi | 20 | 38 | 0 | 38 | completed
Balkh | CF.3b(p)-091-MZR | 3 | Training/Demonstrations Involving Technical Issue on Selected Value Chain in Northern Region. | Training in Saffron VC - Male | Training | 2018-08-08 | 2018-08-08 | Dawlat Abad | 20 | 37 | 0 | 37 | completed
Balkh | CF.3b(q)-092-MZR | 3 | Training/Demonstrations Involving Technical Issue on Selected Value Chain in Northern Region. | Women Food Processing | Training |  |  |  | 20 |  |  |  | completed
Balkh | CF.3b(r)-093-MZR | 3 | Training/Demonstrations Involving Technical Issue on Selected Value Chain in Northern Region. | Saffron Post harvest training | Training | 18/11/18 | 20/11/18 | Balkh, Nahre-e-Shahi, Dehdadi, Dawlat Abd, Khulm, Charketnt, Charbolak | 20 | 15 | 26 | 41 | completed
Balkh | CF.3b(s)-094-MZR | 3 | Training/Demonstrations Involving Technical Issue on Selected Value Chain in Northern Region. | This budget was used with activity 93 for saffron training. | Training | 18/11/18 | 20/11/18 | Balkh | 20 | Beneficiaries are already reported in activity 93 |  |  | completed
Balkh | CF.3b(t)-095-MZR | 3 | Training/Demonstrations Involving Technical Issue on Selected Value Chain in Northern Region. | This budget was used with activity 93 for saffron training. Almond roundtable conducted 15 October, 2019 -Samangan province | Training |  |  |  | 20 |  |  |  | completed
Balkh | CF.3b(u)-096-MZR | 3 | Training/Demonstrations Involving Technical Issue on Selected Value Chain in Northern Region. | Food processing training | Training | 2018-02-10 | 2018-03-10 |  | 20 | 0 | 24 | 24 | completed
Balkh | CF.3b(v)-097-MZR | 3 | Training/Demonstrations Involving Technical Issue on Selected Value Chain in Northern Region. | Food processing training Food Processing - Samangan Expected date August 21, 19 Food processing training - Smanagan province 25 participants | Training | 28/08/19 | 28/08/19 | Center | 20 | 0 | 19 | 19 | completed
Balkh | CF.3b(w)-098-MZR | 3 | Training/Demonstrations Involving Technical Issue on Selected Value Chain in Northern Region. | Food processing training | Training | 30/7/2018 | 31/7/2018 | Dehdadi, Balkh, andNahre-e-Shaihi | 20 | 29 | 0 | 29 | completed
Balkh | CF.3b(x)-99-MZR | 3 | Training/Demonstrations Involving Technical Issue on Selected Value Chain in Northern Region. | Food processing training | Training | 2018-01-08 | 2018-01-02 | Dehdadi, Balkh, andNahre-e-Shaihi | 20 | 29 | 0 | 29 | completed
Balkh | CF.3b(y)-100-MZR | 3 | Training/Demonstrations Involving Technical Issue on Selected Value Chain in Northern Region. | Food processing training | Training |  |  |  | 20 |  |  |  | completed
Balkh | C7.3c(d)-106-MZR | 3 | Internal Exposure Visit for Farmers on selected Value Chains - Northern Zone | Ag-fair attended in Herat (Saffron, Honey & Grapes) | exposure visit | 15/08/18 | 16/08/18 | Center | 10 | 6 | 0 | 6 | completed
Herat | C8.3b(u)-069-HER | 3 | Training/Demonstrations Involving Technical Issue on Selected Value Chain in Western Region. | Grapes VC 2.Post harvest trainings in grapes value chain July,19 3. Faizai accomodation charges July, 19 | Training | 30.July.2018 | 30.July.2018 | Kharuk | 30 | 32 | 0 | 32 | completed
Herat | C8.3b(v)-070-HER | 3 | Training/Demonstrations Involving Technical Issue on Selected Value Chain in Western Region. | Grapes VC 2.Post harvest trainings in grapes value chain July,19 | Training | 31.July.2018 | 31.July.2018 | Pashtoon Zarghon | 20 | 32 | 0 | 32 | completed
Herat | C8.3b(w)-071-HER | 3 | Training/Demonstrations Involving Technical Issue on Selected Value Chain in Western Region. | Grapes VC 2. Post harvest trainings in grapes value chain July,19 | Training | 17.07.18 | 17.07.18 | Guzara | 20 | 36 | 0 | 36 | completed
Herat | C8.3b(x)-072-HER | 3 | Training/Demonstrations Involving Technical Issue on Selected Value Chain in Western Region. | Grapes VC - ANHDO colleagues accomodation charges in Balkh July, 19 | Training | 16.07.18 | 16.07.18 | Injil | 20 | 35 | 0 | 35 | completed
Herat | C8.3b(y)-073-HER | 3 | Training/Demonstrations Involving Technical Issue on Selected Value Chain in Western Region. | Grapes VC and Operation plan Workshop | Training | 29.July.2018 | 29.July.2018 | Zenda Jan | 20 | 31 | 0 | 31 | completed
Herat | C8.3b(z)-074-HER | 3 | Training/Demonstrations Involving Technical Issue on Selected Value Chain in Western Region. | 1.Food processing (Badghis) 2. This budget will be also used for the planned training in food processing in HRT (7th May, 2019) 3. Post harvest trainings in grapes value chain July,19 | Training | 29/01/12 | 2019-03-02 |  | 20 | Budget was shared with activity 98, it was reused train 13 best performing processors on 7th May 2019 |  |  | completed
Herat | CG.3b(a)-075-HER | 3 | Training/Demonstrations Involving Technical Issue on Selected Value Chain in Western Region. | Establishing Saffron processing centers and post-harvest trainings | Training | 31/10/18 | 2018-10-11 | Zenda Jan, Injil, Pashtun Zargun and Ghoryan | 20 | 0 | 126 |  | completed
Herat | CG.3b(b)-076-HER | 3 | Training/Demonstrations Involving Technical Issue on Selected Value Chain in Western Region. | Establishing Saffron processing centers and post-harvest trainings | Training |  |  |  | 20 |  |  |  | completed
Herat | CG.3b(c)-077-HER | 3 | Training/Demonstrations Involving Technical Issue on Selected Value Chain in Western Region. | Establishing Saffron processing centers and post-harvest trainings | Training |  |  |  | 20 |  |  |  | completed
Herat | CG.3b(d)-078-HER | 3 | Training/Demonstrations Involving Technical Issue on Selected Value Chain in Western Region. | Establishing Saffron processing centers and post-harvest trainings | Training |  |  |  | 20 |  |  |  | completed
Herat | CG.3b(e)-079-HER | 3 | Training/Demonstrations Involving Technical Issue on Selected Value Chain in Western Region. | Establishing Saffron processing centers and post-harvest trainings | Training |  |  |  | 20 |  |  |  | completed
Herat | CG.3b(f)-080-HER | 3 | Training/Demonstrations Involving Technical Issue on Selected Value Chain in Western Region. | Establishing Saffron processing centers and post-harvest trainings | Training |  |  |  | 20 |  |  |  | completed
Herat | CG.3b(g)-081-HER | 3 | Training/Demonstrations Involving Technical Issue on Selected Value Chain in Western Region. | Food processing training | Training | 2018-04-09 | 2018-05-09 | Zenda Jan, Injil, Karukh, Pashtoon Zarghon | 20 | 0 | 73 | 73 | completed
Herat | CG.3b(h)-082-HER | 3 | Training/Demonstrations Involving Technical Issue on Selected Value Chain in Western Region. | Food processing training | Training | 2018-06-09 | 2018-07-09 |  | 20 |  |  |  | completed
Herat | CG.3b(i)-083-HER | 3 | Training/Demonstrations Involving Technical Issue on Selected Value Chain in Western Region. | Food processing training | Training | 2018-06-09 | 2018-07-09 |  | 20 |  |  |  | completed
Herat | CG.3b(j)-084-HER | 3 | Training/Demonstrations Involving Technical Issue on Selected Value Chain in Western Region. | Establishing Saffron processing centers | Training | 31/10/18 | 2018-10-11 | Refer to activities 75-80 | 20 | 0 | 0 | Refer to activities 75-80 | completed
Herat | CG.3b(k)-085-HER | 3 | Training/Demonstrations Involving Technical Issue on Selected Value Chain in Western Region. | .Establishing Saffron processing centers >A Saffron Processing Center Roundtable Workshop was organized in Herat city on 10th February 2019. > The planned food frocessing training conducted on 22 & 23 July, 2019 to 11 food processors | Training |  |  |  | 20 |  |  |  | completed
Herat | CG.3b(l)-086-HER | 3 | Training/Demonstrations Involving Technical Issue on Selected Value Chain in Western Region. | Food processing training ( 3 days) | Training | 22/12/18 | 24/12/18 |  | 20 | 0 | 35 | 35 | completed
Herat | C8.3c(d)-087-HER | 3 | Interanal Exposure Visit for Western Farmers On Selected Value Chains | Honey bee consultation workshop from Badghis | exposure visit | 2018-06-08 | 2018-08-08 |  | 10 | 15 | 0 | 15 | completed
Herat | C8.3c(e)-088-HER | 3 | Interanal Exposure Visit for Western Farmers On Selected Value Chains |  | exposure visit | 28/8/18 | 31/08/18 |  | 10 | 9 | 0 | 9 | completed
Herat | C8.3c(f)-089-HER | 3 | International Exposure Visit for Western Farmers on Selected Value Chains. | Preparatory workshop and travel expenses from Kabul to Herat (Jazayeri and Habbi) - Uzbekistan Rasin value chain On 13th November 2019 a follow-up workshop was organized in regards to the Uzbekistan exposure visit in grapes value chain | exposure visit | 24/09/19 | 2019-01-10 |  | 10 | 10 | 0 | 10 | completed
Herat | C8.3c(g)-090-HER | 3 | Support to MAIL/PAIL Ag-fairs in Western regions | Exhibation Grapes VC | ag-fari | 15/08/18 | 16/08/18 |  | 400 |  |  |  | completed
Herat | C8.3f(c)-098-HER | 3 | Training in selected VC to selected stakeholders | Food processing ( for Badghis beneficaireis in HRT) in the same budget on 22nd Feb,19 ( 42) female were also trained in food processing activities. | Training | 29/01/19 | 2019-02-02 |  | 25 | 0 | 33 | 33 | completed
Herat | C8.3f(e)-100-HER | 3 | Training/workshop in selected Vcs to relevant VC stakeholders | Internal Planning workshop held in Mazar (Mr. Dowlaty's travel and accomodation charges) Planned training in food processsing conducted on 9 & 10 July, 2019 to 14 food processors | Training | 2019-09-07 | 2019-10-07 |  | 25 | 0 | 14 | 14 | completed
Nangarhar | C6.3b(m)-063-JAA | 3 | Technical practical trainings on (pre and post harvest, cooperative management, investment and business plan) in onion vc. | Onin VC - Post harvest | Training | 25/6/18 | 25/6/18 | Gushta & Kama | 15 | 18 | 0 | 18 | completed
Nangarhar | C6.3b(n)-064-JAA | 3 | Technical practical trainings on (pre and post harvest, cooperative management, investment and business plan) in onion vc. | Onin VC - Post harvest | Training | 26/6/18 | 26/6/18 | Rodat and Surkhroad | 15 | 21 | 0 | 21 | completed
Nangarhar | C6.3b(o)-065-JAA | 3 | Technical practical trainings on (pre and post harvest, cooperative management, investment and business plan) in onion vc. | Onion VC (charged HRT planning sessions). Post havest losses training in onion VC | Training | 2018-11-09 | 2018-11-09 |  | 15 | 23 | 0 | 23 | completed
Nangarhar | C6.3b(p)-066-JAA | 3 | Technical practical trainings on (pre and post harvest, cooperative management, investment and business plan) in onion vc. | Onin VC - Post harvest | Training | 27/6/18 | 27/6/18 | Kuz Kunar | 15 | 21 | 0 | 21 | completed
Nangarhar | C6.3b(r)-068-JAA | 3 | Technical practical trainings on (pre and post harvest, cooperative management, investment and business plan) in Beekeeping vc | Post-harvest lossess training . Technical training on pest and diseases and agro chemical application (09, 10,13,14,15.04.19_ Surkhroad Kuz Kunar, Rodat, Goshta, Kama districts. In each aftermentioned district 10 farmers were trained on subject matter) | Training | 2018-12-09 | 2018-12-09 |  | 15 | 31 | 0 | 31 | completed
Nangarhar | C6.3b(s)-069-JAA | 3 | Technical practical trainings on (pre and post harvest, cooperative management, investment and business plan) in onion vc | One day trianing in each site was conduted on onin VC - Raised Beds. IN each day 10 participants were trained on subject matter. | Training | 29/01/19 | 30/01/19 | Gushta, Kama, Kuz Kunar, Rodat and Surkhrod | 15 | 50 | 0 | 50 | completed
Nangarhar | C6.3b(t)-070-JAA | 3 | Technical practical trainings on (pre and post harvest, cooperative management, investment and business plan) in Beekeeping vc. | Food processing training Feb 2019 Food Processing Training July, 2019 | Training |  |  |  | 15 |  |  |  | completed
Nangarhar | C6.3b(u)-071-JAA | 3 | Technical practical trainings on (pre and post harvest, cooperative management, investment and business plan) in Beekeeping vc. | One day Practical training on Quen production was conducted to 60 different beekeepers. Each day 20 participants were trainined on subject matter. | Training | 2019-01-04 | 2014-03-04 | Different districts | 15 | 60 | 0 | 60 | completed
Nangarhar | C6.3b(v)-072-JAA | 3 | Technical practical trainings on (pre and post harvest, cooperative management, investment and business plan) in Beekeeping vc. | Food Processing | Training | 17/12/18 | 19/12/18 | Behsood, Surkhroad, Kuz- Kunar, Kama districts and Jalalabad | 15 | 0 | 16 | 16 | completed
Nangarhar | C6.3b(w)-073-JAA | 3 | Techinical trainings food processing to woment groups in Nangahar province. | Food Processing Training in Bamyan | Training | 17/08/18 | 17/08/18 |  | 15 | 0 | 24 | 24 | completed
Nangarhar | C6.3b(x)-074-JAA | 3 | Techinical trainings food processing to woment groups in Nangahar province. | Food Processing Training in Bamyan (usd up) | Training | 18/08/18 | 18/08/18 |  | 15 |  |  |  | completed
Nangarhar | C6.3b(y)-075-JAA | 3 | Techinical trainings food processing to woment groups in Nangahar province. | Food processing training in Nangarhar | Training | 24/9/18 | 26/09/18 | Behsood, Surkhroad, Kuz- Kunar, Kama districts and Jalalabad | 15 | 0 | 15 | 15 | completed
Nangarhar | C6.3b(z)-076-JAA | 3 | Techinical trainings food processing to woment groups in Nangahar province. | Training in onion VC - raise bed nursery | Training | 2018-06-11 | 2018-06-11 | Goashta, Rodat, and Kuz Kunar | 15 | 25 | 0 | 25 | completed
Nangarhar | CE.3b(a)-077-JAA | 3 | Techinical trainings food processing to woment groups in Nangahar province. | Training in onion VC - raise bed nursery | Training | 2018-07-11 | 2018-07-11 | Kama and Surk Rod | 15 | 25 | 0 | 25 | completed
Nangarhar | C6.3c(d)-082-JAA | 3 | Conduct exposure visit with in the country on selected Vcs | Attended Herat festival (Saffron, Grapes & Honey) | exposure visit | 15/08/2018 | 16/08/2018 |  | 30 | 4 | 0 | 4 | completed
Kabul | C5.3b(r)-091-KBL | 3 | Technical practical trainings (Pre and post-harvest, cooperative management, investment and business plan) in each VCs | Food processing training | Training | 2018-11-12 | 2018-12-12 | Different locations | 30 | 0 | 38 | 38 | completed
Kabul | C5.3b(s)-092-KBL | 3 | Technical practical trainings (Pre and post-harvest, cooperative management, investment and business plan) in each VCs | Food processing training | Training | 14/05/18 | 15/05/18 | Paghman, Guldara, Shakerdara, Logar, Char asyab, Kapisa, Panjsheer, and Qara Bagha | 30 | 0 | 30 | 30 | completed
Kabul | C5.3b(t)-093-KBL | 3 | Technical practical trainings (Pre and post-harvest, cooperative management, investment and business plan) in each VCs | Food processing training | Training |  |  |  | 30 |  |  |  | completed
Kabul | C5.3b(u)-094-KBL | 3 | Technical practical trainings (Pre and post-harvest, cooperative management, investment and business plan) in each VCs | Food processing training Also will be used for a workshop (Proposed improvement of the home economy Badagham in collobration forestery depart, private sect and UNDP) 16 July, 2019 | Training | 16/07/19 | 16/07/19 |  | 30 | 20 | 5 | 25 | completed
Kabul | C5.3b(v)-095-KBL | 3 | Technical practical trainings (Pre and post-harvest, cooperative management, investment and business plan) in each VCs | Apple VC post harvest activities | Training | 31/07/2018 | 31/07/2018 | Paghman | 30 |  |  |  | completed
Kabul | C5.3b(w)-096-KBL | 3 | Technical practical trainings (Pre and post-harvest, cooperative management, investment and business plan) in each VCs | Apple VC - Pruning workshop | Training | 16/04/2019 | 17/04/2019 | Farza, Paghman, Jalriz, Shakardara, Maidan Shar (Wardak Province) | 30 | 42 | 0 | 42 | completed
Kabul | C5.3b(x)-097-KBL | 3 | Technical practical trainings (Pre and post-harvest, cooperative management, investment and business plan) in each VCs | Apple Thinning, Green pruning and IPM Training | Training | 26.06.19 and | 30.06.19 | Guldara | 30 | 38 | 0 | 38 | completed
Kabul | C5.3b(y)-098-KBL | 3 | Technical practical trainings (Pre and post-harvest, cooperative management, investment and business plan) in each VCs | Technical training to vineyard farmers the green pruning and IPM | Training | 24.06.19 | 25.06.19 | Mirbachakot | 30 | 42 | 0 | 42 | completed
Kabul | CD.3b(a)-100-KBL | 3 | Technical practical trainings (Pre and post-harvest, cooperative management, investment and business plan) in each VCs | A pre-harvest training in grapes VC | Training | 19/03/19 | 19/03/19 | Guldara | 30 | 25 | 0 | 25 | completed
Kabul | CD.3b(b)-101-KBL | 3 | Technical practical trainings (Pre and post-harvest, cooperative management, investment and business plan) in each VCs | Women Food Processing | Training | 24/07/18 | 25/07/18 | Chahar Asyab, Sorobi, Mirbacha Kot, Guldara, Qarabagh districts of Kabul and also Parwan and Logar Provinces | 30 | 0 | 27 | 27 | completed
Kabul | CD.3b(c)-102-KBL | 3 | Technical practical trainings (Pre and post-harvest, cooperative management, investment and business plan) in each VCs | Women Food Processing | Training |  |  |  | 30 |  |  |  | completed
Kabul | C5.3c(d)-105-KBL | 3 | Internal country exposure visit for central region farmers on selected VCs | Bamyan Field Visit by team for exploring different business opportunities | exposure visit | 2018-08-28 | 2018-09-02 |  | 10 | 3 | 0 | 3 | completed
Kabul | C5.3c(e)-106-KBL | 3 | International country exposure visit for central region farmers and traders on grape value chain in India | >planning workshop (13, Nov,18), Exposure visit with 15 different stakeholders >Exposure visit took place -India from 18/02/19 - 26/02/19 (9 farmers) > A Post- Exposure Visit Dissemination Workshop was held in Herat province on 26 March to share the results and lessons learned from the Exposure Visit to India which was undertaken by Kabul Team of EU FARM in Feb 2019 >A Post- Exposure Visit Dissemination Workshop was held in Kabul province on 12 March to share the results and lessons learned from the Exposure Visit to India | exposure visit | 13/11/18 | 13/11/18 |  | 10 | 0 | 15 | 15 | completed
Kabul | C5.3c(f)-107-KBL | 3 | International country exposure visit for central region farmers and traders on apple value chain in Turkey | India On 6th November 2019 a follow-up workshop was organized on the exposure visit to India at apple value chain. | exposure visit | 16/10/2019 | 26/10/19 |  | 10 | 9 | 1 | 10 | completed
Kabul | C5.3f(c)-109-KBL | 3 | Training in selected VC to selected stakeholders | Used for the food processing activity - Branding and Packaging | Training | 25.06.19 | 27.06.19 | Kapisa, Parwan, Panjsher and Kabul | 30 | 26 | 0 | 26 | completed
Kabul | C5.3f(d)-110-KBL | 3 | Training in selected VC to selected stakeholders | On 19th November 2019 forward and backward business linkage event was arranged | Training | 19/11/19 | 19/11/19 |  | 30 | 0 | 15 | 15 | completed
Kabul | C5.4c(a)-111-KBL | 3 | Printing of extension related materials | Printing of receipes to the food processing beneficiaries | services |  |  |  | Not applicable |  |  |  | completed
Helmand | C1.1b(c)-032-HEL | 1 | The aim of this activity is to held second quarterly provincial committee meeting on sub-national level for coordination, informing this committee regarding progress of FARM project, problem in VC, Market, and reduce the duplication of activities in the south by other NGOs. The core stakeholder during this meeting is DAIL director, DRRD director, DoCN, DoE, Provincial Sectorial director, women affair director, district extension officers, farmers and traders associations chairman, key input suppliers and traders. | keep it | PC meeting | 17-07-19 | 17-07-19 |  | 40 | 45 | 0 | 45 | completed
Kandahar | C1.1b(c)-028-KND | 1 | The aim of this activity is to held second quarterly provincial committee meeting on sub-national level for coordination, informing this committee regarding progress of FARM project, problem in VC, Market, and reduce the duplication of activities in the south by other NGOs. The core stakeholder during this meeting is DAIL director, DRRD director, DoCN, DoE, Provincial Sectorial director, women affair director, district extension officers, farmers and traders associations chairman, key input suppliers and traders. | Keep it | PC meeting | 2019-02-14 | 2019-02-14 | City Center | 40 | 33 | 0 | 33 | completed
Kandahar | C1.1b(d)-029-KND | 1 | The aim of this activity is to held 3rd quarterly provincial committee meeting on sub-national level for coordination, informing this committee regarding progress of FARM project, problem in VC, Market, and reduce the duplication of activities in the south by other NGOs. The core stakeholder during this meeting is DAIL director, DRRD director, DoCN, DoE, Provincial Sectorial director, women affair director, district extension officers, farmers and traders associations chairman, key input suppliers and traders. |  | PC meeting | 2018-04-07 | 2018-04-07 |  | 40 | 27 | 0 | 27 | completed
Kandahar | C1.1b(e)-030-KND | 1 | The aim of this activity is to held 4th quarterly provincial committee meeting on sub-national level for coordination, informing this committee regarding progress of FARM project, problem in VC, Market, and reduce the duplication of activities in the south by other NGOs. The core stakeholder during this meeting is DAIL director, DRRD director, DoCN, DoE, Provincial Sectorial director, women affair director, district extension officers, farmers and traders associations chairman, key input suppliers and traders. | keep it | PC meeting | 24-07-19 | 24-07-19 |  | 40 | 33 | 0 | 33 | completed
Kandahar | C3.1b(e)-032-KND | 3 | Conduct district development agriculture plan workshop on provincial level during this workshop all stakeholders from targeted district will attend to discuss the current status of district agriculture development plan and review how to address the constraints. |  | Workshop | 2019-02-05 | 2019-02-05 | Center | 40 | 35 | 0 | 35 | completed
Helmand | C3.1b(c)-036-HEL | 3 | Conduct district development agriculture plan workshop on provincial level during this workshop all stakeholders from targeted district will attend to discuss the current status of district agriculture development plan and review how to address the constraints. |  | Workshop | 2019-02-05 | 2019-02-05 | Center | 40 | 40 | 0 | 40 | completed
Kandahar | C3.1b(f)-033-KND | 3 | Two days training on district agriculture development plan to PAIL staff, district agriculture staff, DDA, CDC, CSOs, district municipality department staff, district development cluster, traders, input suppliers, lead farmers, ALA, statistical department and NHLP extension workers ( 40 stakeholders) |  | Workshop | 16-04-19 | 17-04-19 | Center | 40 | 38 | 0 | 38 | completed
Helmand | C3.1b(d)-037-HEL | 3 | Two days training on district agriculture development plan to PAIL staff, district agriculture staff, DDA, CDC, CSOs, district municipality department staff, district development cluster, traders, input suppliers, lead farmers, ALA, statistical department and NHLP extension workers ( 40 stakeholders) |  | Training | 16-04-19 | 17-04-19 | Center | 40 | 40 | 0 | 40 | completed
Helmand | C3.1b(e )-038-HEL | 3 | Two days workshop on the development of district agriculture plan with the active participation of PAIL staff, district agriculture staff, DDA, CDC, CSOs, district municipality department staff, district development cluster, traders, input suppliers, lead farmers, ALA, statistical department and NHLP extension workers ( 30 stakeholders) |  | Training | 21-05-19 | 23-05-19 | Center | 30 | 30 | 0 | 30 | completed
Kandahar | C3.1b(g)-034-KND | 3 | Two days workshop on the development of district agriculture plan with the active participation of PAIL staff, district agriculture staff, DDA, CDC, CSOs, district municipality department staff, district development cluster, traders, input suppliers, lead farmers, ALA, statistical department and NHLP extension workers ( 30 stakeholders) | Two Days Workshop on Development of District Agriculture Plan for Arghandab, Kandahar | Workshop | 21-05-19 | 22-05-19 | Center | 30 | 30 | 0 | 30 | completed
Kandahar | C3.1b(h)-080-KND | 3 | Two days training on district agriculture development plan to PAIL staff, district agriculture staff, DDA, CDC, CSOs, district municipality department staff, district development cluster, traders, input suppliers, lead farmers, ALA, statistical department and NHLP extension workers ( 30 stakeholders) |  | Training | 18/06/19 | 18/06/19 | Center | 30 | 30 | 0 | 30 | completed
Kandahar | C3.2a(b)-035-KND | 3 | Identification of the key 5-10 key input suppliers in selected VCs. 3 MoU will be signed with these interested and key input suppliers with grape and pomegranate producers in Kandahar Province. Facilitation of one meeting for the purpose of development and signing of MoUs between privet Potential entrepreneurs. At least 3 input suppliers will be selected to sign MoUs with 6-10 potential producers in selected value chains. |  | signing MoU |  | 2019-03-13 | Kandahar City | 1900-01-09 |  | 22 | 22 | completed
Helmand | C3.2a(b)-041-HEL | 3 | Identification of the key 5-10 key input suppliers in selected VCs. 2 MoU will be signed with these interested and key input suppliers with grape and pomegranate producers in Helmand Province. Facilitation of one meeting for the purpose of development and signing of MoUs between privet Potential entrepreneurs.At least 3 input suppliers will be selected to sign MoUs with 6-10 potential producers in selected value chains. |  | signing MoU |  | 2019-03-19 | Center | 10 |  | 30 | 30 | completed
Kandahar | C3.2b(b)-036-KND | 3 | This training will be for two days according to the suggestion of DAIL and input suppliers association from all targeted districts of Kandahar province to 35-40 input suppliers. | 2 Days capacity building training to Agro-input Suppliers in Kandahar | Training | 2018-07-17 | 2018-07-18 | Center | 40 | 40 | 0 | 40 | completed
Kandahar | C3.2b(c)-037-KND | 3 | Conduct two days training on development of business plan to 10 potential private sector stakeholders including input suppliers, traders companies, cold storage and processing companies. |  | Training | 17/07/18 | 18/07/18 | City Center | 10 | 12 | 0 | 12 | completed
Kandahar | C3.2b(d)-038-KND | 3 | 8 input supplier, processors, traders and potential producers in grape and pomegranate value chain participated in study tour to Herat Province. |  | Training | 13 | 13/08/18 | 14/08/18 | 8 | 5 | 0 | 5 | completed
Helmand | C3.2b(d)-044-HEL | 3 | 8 input supplier, processors, traders and potential producers in grape and pomegranate value chain participated in study tour to Herat Province. | Study Tours of “FARM” Helmand Stakeholders to Herat Province | Training | 15/08/18 | 16/08/18 | Lashkar Gah,Nahr-e-Saraj | 8 | 6 | 0 | 6 | completed
Kandahar | C3.1b(h)-039-KND | 3 | 1 roundtable meeting conducted in newly selected district of Panjwayee with 35 stakeholders including district governor, district DAIL extension department staff, DDA members and government line department staff and private sectors. |  | Round table |  |  | Center | 35 |  |  |  | completed
Helmand | C3.1b(h)-45-HEL | 3 | 1 roundtable meeting conducted in newly selected district of Panjwayee with 35 stakeholders including district governor, district DAIL extension department staff, DDA members and government line department staff and private sectors. |  | Round table |  |  | Center | 35 |  |  |  | completed
Kandahar | C3.3b(c)-040-KND | 3 | Conduct 1 day PHHT to 50 farmers and traders in grape value chain. This training will be conducted in the grape vineyard field. The topics in this training will be including ( harvesting techniques, pre- cooling, cleaning, sorting, grading, packing, labeling and transportation procedure). |  | Training | 2018-07-30 | 2018-07-30 | Panjwayi | 50 | 50 | 0 | 50 | completed
Kandahar | C3.3b(d)-041-KND | 3 | Conduct 1 day PHHT to 50 farmers and traders in grape value chain. This training will be conducted in the grape vineyard field. The topics in this training will be including ( harvesting techniques, pre- cooling, cleaning, sorting, grading, packing, labeling and transportation procedure). | Post-Harvest handling training on grapes value chain in Daman District-Kandahar. | Training | 2018-12-08 | 13/08/18 | Center | 50 | 50 | 0 | 50 | completed
Kandahar | C3.3b(e)-042-KND | 3 | Conduct 1 day PHHT to 50 farmers and traders in grape value chain. This training will be conducted in the grape vineyard field. The topics in this training will be including ( harvesting techniques, pre- cooling, cleaning, sorting, grading, packing, labeling and transportation procedure). | Post-Harvest handling training on Melons value chain in Spinboldak District-Kandahar. | Training | 17/09/18 | 17/09/18 | Spinboldak | 50 | 49 | 0 | 49 | completed
Kandahar | C3.3b(f)-043-KND | 3 | Conduct 1 day PHHT to 50 farmers and traders in grape value chain. This training will be conducted in the grape vineyard field. The topics in this training will be including ( harvesting techniques, pre- cooling, cleaning, sorting, grading, packing, labeling and transportation procedure). | Post-Harvest Handling Training on Pomegranate Value Chain in Arghandab District, Kandahar. | Training | 43373 | 2018-10-01 | Center | 50 | 50 | 0 | 50 | completed
Kandahar | C3.3b(g)-044-KND | 3 | Conduct 1 day PHHT to 50 farmers and traders in grape value chain. This training will be conducted in the grape vineyard field. The topics in this training will be including ( harvesting techniques, pre- cooling, cleaning, sorting, grading, packing, labeling and transportation procedure). | Post-Harvest Handling Training on Pomegranates in Panjwayi District, Kandahar. | Training | 2018-08-10 | 2018-08-10 | Center | 50 | 48 | 0 | 48 | completed
Kandahar | C3.3b(h)-045-KND | 3 | Conduct 1 day PHHT to 50 farmers and traders in grape value chain. This training will be conducted in the grape vineyard field. The topics in this training will be including ( harvesting techniques, pre- cooling, cleaning, sorting, grading, packing, labeling and transportation procedure). | Post-Harvest Handling Training on Pomegranates Value Chain in Dand District, Kandahar. | Training | 16/10/18 | 16/10/18 | Center | 50 | 50 | 0 | 50 | completed
Kandahar | C3.3b(i)-046-KND | 3 | Conduct 1 day PHHT to 50 farmers and traders in grape value chain. This training will be conducted in the grape vineyard field. The topics in this training will be including ( harvesting techniques, pre- cooling, cleaning, sorting, grading, packing, labeling and transportation procedure). | Post-Harvest Handling Training on Pomegranates Value Chain in Daman District, Kandahar. | Training | 30/10/18 | 30/10/18 | Center | 50 | 44 | 0 | 44 | completed
Kandahar | C3.3b(j)-047-KND | 3 | Conduct 1 day PHHT to 50 farmers and traders in grape value chain. This training will be conducted in the grape vineyard field. The topics in this training will be including ( harvesting techniques, pre- cooling, cleaning, sorting, grading, packing, labeling and transportation procedure). | Post-Harvest Handling Training on Grapes/Raisins in Panjwayee District- Kandahar | Training | 2019-07-08 | 2019-07-08 | Center | 50 | 50 | 0 | 50 | completed
Kandahar | C3.3b(k)-048-KND | 3 | Conduct 1 day PHHT to 50 farmers and traders in grape value chain. This training will be conducted in the grape vineyard field. The topics in this training will be including ( harvesting techniques, pre- cooling, cleaning, sorting, grading, packing, labeling and transportation procedure). | Post-Harvest handling training on Melons value chine in central Districts-Kandahar. | Training | 28/08/19 | 28/08/19 | Center | 50 | 50 | 0 | 50 | completed
Kandahar | C3.3b(I)-049-KND | 3 | Conduct 1 day PHHT to 50 farmers and traders in grape value chain. This training will be conducted in the grape vineyard field. The topics in this training will be including ( harvesting techniques, pre- cooling, cleaning, sorting, grading, packing, labeling and transportation procedure). | Post-Harvest Handling Training on Grapes/Raisins in Argandab District- Kandahar | Training | 2019-05-09 | 2019-05-09 | Center | 50 | 50 | 0 | 50 | completed
Kandahar | C3.3b(m)-050-KND | 3 | Conduct 1 full day PHHT to 50 farmers and traders in pomegranate value chain. This training will be conducted in the pomegranate field. The topics in this training will be including (land preparation, new orchards establishment, pruning, soil management, fertilizer application, irrigation, weeding, pest and diseases control). |  | Training | 2019-02-21 | 2019-02-21 | Spinboldak | 50 |  | 47 | 47 | completed
Kandahar | C3.3b(n)-051-KND | 3 | Conduct 1 full day PHHT to 50 farmers and traders in pomegranate value chain. This training will be conducted in the pomegranate field. The topics in this training will be including (land preparation, new orchards establishment, pruning, soil management, fertilizer application, irrigation, weeding, pest and diseases control). |  | Training | 2019-02-27 | 2019-02-27 | Daman | 50 |  | 50 | 50 | completed
Kandahar | C3.3b(o)-052-KND | 3 | Conduct 1 full day PHHT to 50 farmers and traders in pomegranate value chain. This training will be conducted in the pomegranate field. The topics in this training will be including (land preparation, new orchards establishment, pruning, soil management, fertilizer application, irrigation, weeding, pest and diseases control). |  | Training | 2019-03-05 | 2019-03-05 | Panjwayi | 50 |  | 49 | 49 | completed
Kandahar | C3.3b(p)-053-KND | 3 | Conduct 1 full day PHHT to 50 farmers and traders in grape value chain. This training will be conducted in the grape field. The topics in this training will be including (land preparation, new orchards establishment, pruning, fertilizer application, irrigation, weeding, pest and diseases control). | Post-Harvest handling training on grapes value chine in Zhari District-Kandahar. | Training | 2019-09-17 | 2019-09-17 | Center | 50 | 50 | 0 | 50 | completed
Kandahar | C3.3b(q)-054-KND | 3 | Conduct 1 full day PHHT to 50 farmers and traders in grape value chain. This training will be conducted in grape field. The topics in this training will be including (land preparation, new orchards establishment, pruning, fertilizer application, irrigation, weeding, pest and diseases control). | Post-Harvest Handling Training on Pomegranates in Zhari District, Kandahar. | Training | 16/10/19 | 16/10/19 | Center | 50 | 49 | 0 | 49 | completed
Helmand | C3.3b(c)-046-HEL | 3 | Conduct 1 day PHHT to 50 farmers and traders in grape value chain. This training will be conducted in the grape vineyard field. The topics in this training will be including ( harvesting techniques, pre- cooling, cleaning, sorting, grading, packing, labeling and transportation procedure). | Post-Harvest Handling Training on Grapes in Lashkar Gah District- Helmand | Training | 2018-11-07 | 2018-11-07 | City Center | 50 | 49 | 0 | 49 | completed
Helmand | C3.3b(d)-047-HEL | 3 | Conduct 1 day PHHT to 50 farmers and traders in grape value chain. This training will be conducted in the grape vineyard field. The topics in this training will be including ( harvesting techniques, pre- cooling, cleaning, sorting, grading, packing, labeling and transportation procedure). | Farmers Pre-Harvest Management Training in Grape Value Chain of Nawa-i-Barakzayi District- Helmand | Training | 26/06/18 | 26/06/18 | Naw-e-Barkzai | 50 | 50 | 0 | 50 | completed
Helmand | C3.3b(e )-048-HEL | 3 | Conduct 1 day PHHT to 50 farmers and traders in grape value chain. This training will be conducted in the grape vineyard field. The topics in this training will be including ( harvesting techniques, pre- cooling, cleaning, sorting, grading, packing, labeling and transportation procedure). | Post-harvest handling training on grapes in Gramesir District | Training | 2018-08-08 | 2018-08-08 | Graemsir | 50 | 41 | 0 | 41 | completed
Helmand | C3.3b(f)-049-HEL | 3 | Conduct 1 day PHHT to 50 farmers and traders in grape value chain. This training will be conducted in the grape vineyard field. The topics in this training will be including ( harvesting techniques, pre- cooling, cleaning, sorting, grading, packing, labeling and transportation procedure). | Post-Harvest Handling Training on Grapes in Nahr-e-Saraj District- Helmand | Training | 16/08/18 | 16/08/18 | Nahr-e-Saraj | 50 | 50 | 0 | 50 | completed
Helmand | C3.3b(g)-050-HEL | 3 | Conduct 1 day PHHT to 50 farmers and traders in Pomegranate value chain. This training will be conducted in the Pomegranate vineyard field. The topics in this training will be including ( harvesting techniques, pre- cooling, cleaning, sorting, grading, packing, labeling and transportation procedure). | Post-Harvest Handling Training on Grapes Value Chain in Nawa-e-Barakzai District, Helmand | Training | 13/09/18 | 13/09/18 | Nawa-e-Barakzyi | 50 | 47 | 0 | 47 | completed
Helmand | C3.3b(h)-051-HEL | 3 | Conduct 1 day PHHT to 50 farmers and traders in Pomegranate value chain. This training will be conducted in the Pomegranate vineyard field. The topics in this training will be including ( harvesting techniques, pre- cooling, cleaning, sorting, grading, packing, labeling and transportation procedure). | Post-Harvest Handling Training on Pomegranate of Nahr-e-Saraj | Training | 2018-09-27 | 2018-09-27 | Center | 50 | 50 | 0 | 50 | completed
Helmand | C3.3b(i)-052-HEL | 3 | Conduct 1 day PHHT to 50 farmers and traders in Pomegranate value chain. This training will be conducted in the Pomegranate vineyard field. The topics in this training will be including ( harvesting techniques, pre- cooling, cleaning, sorting, grading, packing, labeling and transportation procedure). |  | Training | 2018-10-04 | 2018-10-04 | Center | 50 | 50 | 0 | 50 | completed
Helmand | C3.3b(j)-053-HEL | 3 | Conduct 1 day PHHT to 50 farmers and traders in Pomegranate value chain. This training will be conducted in the Pomegranate vineyard field. The topics in this training will be including ( harvesting techniques, pre- cooling, cleaning, sorting, grading, packing, labeling and transportation procedure). | Post-Harvest Handling Training on Pomegranates Value Chain in Nawa-e-Barakzaiy District, Helmand | Training | 16/10/18 | 16/10/18 | Naw-e-Barkzai | 50 | 50 | 0 | 50 | completed
Helmand | C3.3b(k)-054-HEL | 3 | Conduct 1 full day PHHT to 50 farmers and traders in grape value chain. This training will be conducted in the grape field. The topics in this training will be including (land preparation, new orchards establishment, pruning, soil management, fertilizer application, irrigation, weeding, pest and diseases control). | Post-Harvest Handling Training on Pomegranates Value Chain in Garemsir District, Helmand. | Training | 30/10/18 | 30/10/18 | Graemsir | 50 | 50 | 0 | 50 | completed
Helmand | C3.3b(l)-055-HEL | 3 | Conduct 1 full day PHHT to 50 farmers and traders in grape value chain. This training will be conducted in the grape field. The topics in this training will be including (land preparation, new orchards establishment, pruning, soil management, fertilizer application, irrigation, weeding, pest and diseases control). |  | Training |  | 2019-02-19 | Center | 50 |  | 49 | 49 | completed
Helmand | C3.3b(m)-056-HEL | 3 | Conduct 1 full day Pre- HHT to 50 farmers and traders in pomegranate value chain. This training will be conducted in the pomegranate field. The topics in this training will be including (land preparation, new orchards establishment, pruning, soil management, fertilizer application, irrigation, weeding, pest and diseases control). |  | Training |  | 2019-02-27 | Center | 50 |  | 50 | 50 | completed
Helmand | C3.3b(n)-057-HEL | 3 | Conduct 1 full day Pre- HHT to 50 farmers and traders in pomegranate value chain. This training will be conducted in the pomegranate field. The topics in this training will be including (land preparation, new orchards establishment, pruning, soil management, fertilizer application, irrigation, weeding, pest and diseases control). | Post-Harvest Handling Training on Grapes/Raisins in Lashkar Gah District- Helmand | Training | 2019-07-08 | 2019-07-08 | Center | 50 | 50 | 0 | 50 | completed
Kandahar | C3.3c(b)-055-KND | 3 | Conduct one day agriculture inputs and production exhibition fair in close coordination with provincial government line department other NGOs, private sector stakeholders in Kandahar province. During this activity stakeholders will be encouraged to participate from other southern provinces. | Kandahar Ag-Products & Inputs Exhibition 2018 | ag-fair | 13/11/18 | 14/11/18 | Center | 100 | 242 | 34 | 276 | completed
Helmand | C3.3c(c)-58-HEL | 3 | Conduct one day agriculture inputs and production exhibition fair in close coordination with provincial government line department other NGOs, private sector stakeholders in Helmand province. During this activity stakeholders will be encouraged to participate from other southern provinces. |  | ag-fair |  | 2019-11-14 | Center | 100 | 11 | 289 | 300 | completed

## Codes
Component | EUD Approval | Responsible Person | Status | Color | Provinces | Type of Activity | Indicator Number | Components | Measurement Unit
One | Yes | 1 | On-going |  | Badakhshan | Training | 1 | 1899-12-31 | Percentage (%)
Three | No | 2 | Pending |  | Badghis | Visit | 2 | 1900-01-02 | Farmers (No.)
|  | 3 | Completed |  | Baghlan | Workshop | 1.1 |  | Procedures (No.)
|  | 4 | Dropped |  | Balkh | PSC Meeting | 1.2 |  | Model (No.)
|  | 5 |  |  | Bamyan | PC Meeting | 2.1 |  | Agreement (No.)
|  | 6 |  |  | Daykundi | Exposure visit | R1.1 |  | Strategy (No.)
|  | 7 |  |  | Farah | Linkage Meeting | R1.2 |  | Input suppliers (No.)
|  | 8 |  |  | Faryab | Procurement of goods | R.1.3 |  | Committee (No.)
|  | 9 |  |  | Ghazni | Analysis | R1.4 |  | Meetings (No.)
|  | 10 |  |  | Ghor | Policy development | R.3.2 |  | Workshops (No.)
|  | 11 |  |  | Helmand | Materials development | R3.3 |  | Trainings (No.)
|  | 12 |  |  | Herat | Services | R3.4 |  | MAIL staff (No.)
|  | 13 |  |  | Jowzjan | Others | 1.1a.1 |  | Curriculum(No.)
|  | 14 |  |  | Kabul |  | 1.1a.2 |  | PPP (No.)
|  | 15 |  |  | Kandahar |  | 1.1a.3 |  | Persons (No.)
|  | 16 |  |  | Kapisa |  | 1.1b.1 |  | Concept Note (No.)
|  | MC |  |  | Khost |  | 1.1b.2 |  | Research Tours (No.)
|  | 9 & 11 |  |  | Kunar |  | 1.1b.3 |  | Assessment (No.)
|  | 3 & 11 |  |  | Kunduz |  | 1.1b.3.1 |  | Digital Library (No.)
[5 empty] | Laghman |  | 1.1b.3.2 |  | District profiles (No.)
[5 empty] | Logar |  | 1.1.c.1 |  | Value chain (No.)
[5 empty] | Maidan Wardak |  | 1.1d.1 |  | Strategies (No.)
[5 empty] | Nangarhar |  | 1.2a.1 |  | Agriculture plan (No.)
[5 empty] | Nimruz |  | 1.2a.2 |  | Packages (No.)
[5 empty] | Nuristan |  | 1.2b.1 |  | Reforms (No.)
[5 empty] | Paktia |  | 1.2.b.2 |  | Roundtable meetings (No.)
[5 empty] | Paktika |  | 1.2b.3 |  | Visits (No)
[5 empty] | Panjshir |  | 1.2c.1 |  | Study trips (No.)
| Total SNKE days | 400 |  |  | Parwan |  | 1.2c.2 |  | Business Plan
| Total JNKE days | 800 |  |  | Samangan |  | 1.2d.1 |  | Business opportunities (No.)
[5 empty] | Sar-e Pol |  | 1.2d.2 |  | B2B events (No.)
[5 empty] | Takhar |  | 1.2e.1 |  | Regulation doc (No.)
[5 empty] | Urozgan |  | 1.2e.2 |  | Products (No.)
[5 empty] | Zabul |  | 1.3a.1 |  | Success stories
1.3a.1.1
1.3a.2
1.3b.1
1.4a.1
1.4b.2
1.4b2.1
1.4c.3
1.4c.3.1
1.4d.4
1.4d.5
1.4e.6
1.5a.1
1.5a.1.1
1.5b.1
1.5b.2
1.5c.1
3.1a.1
3.1a.2
3.1b.1
3.1b.2
3.1b.3
3.1c.1
3.1c.2
3.1c.3
3.1c.4
3.2a.1
3.2b.1
3.2b.1
3.2b.2
3.3a.1
3.3a.2
3.3b.1
3.3c.1
3.3c.2
3.3d.1
3.3e.1
3.3f.1
3.3f.2
3.3.f.3
3.3g.1
3.3g.2
3.4a.1
3.4b.1
3.4c.1